## Timetable
EVENT TIMETABLE FOR JK | Who Responsible | Days Before | Done By | Comments | Printed on
2020-05-07
Event date -----> |  |  | 2022-04-15 | enter in format dd/mm/yy
BEFORE THE EVENT
Event set-up
Add area to list of embargoed areas | BOF | 720 | 2020-04-25
Written land access permissions all obtained | Organiser | 270 | 2021-07-19
Parking and arena location identified | Organiser | 230 | 2021-08-28
Written parking and arena permissions all obtained | Organiser | 220 | 2021-09-07
Liaise with land owners on environmental issues | Organiser | 220 | 2021-09-07
Land use/parking confirms uploaded to Dropbox folder | Organiser | 220 | 2021-09-07
Organiser notified if WRE | Organiser | 220 | 2021-09-07
Ascertain if any variations to rules to be sought and apply to ECC | Organiser | 220 | 2021-09-07
Wet weather/insufficent access alternative parking considered | Organiser | 220 | 2021-09-07
Power/water needs clarified | Organiser | 120 | 2021-12-16
Consider if tractor may be needed if bad weather and arrange | Organiser | 120 | 2021-12-16
Traders identified | Organiser | 220 | 2021-09-07
Contracts with traders finalised | Organiser | 180 | 2021-10-17
Printer identified | Organiser | 220 | 2021-09-07
Contracts with printer finalised | Organiser | 180 | 2021-10-17
Commentary team identified | Organiser | 180 | 2021-10-17
Contract with commentary team finalised | Organiser | 180 | 2021-10-17
Radio controls team identified | Organiser | 180 | 2021-10-17
Contract with radio controls team finalised | Organiser | 180 | 2021-10-17
Seeding coordinator identified | Organiser | 180 | 2021-10-17
Seeding arrangements agreed | Organiser | 180 | 2021-10-17
Photographer appointed | Organiser | 180 | 2021-10-17
Toilet provider identified | Organiser | 180 | 2021-10-17
Toilets contract finalised | Organiser | 180 | 2021-10-17
Consider local sponsorship opportunities and prepare plan | Organiser | 180 | 2021-10-17
Verify suitability of food traders | Organiser | 180 | 2021-10-17
Identify O equipment traders and verify suitability | Organiser | 180 | 2021-10-17
Massage service provider identified and basis agreed | Organiser | 150 | 2021-11-16
Draft arena plan | Organiser | 150 | 2021-11-16
Officials and manpower
Organisers identified |  |  | Done
Planners identified | Association | 450 | 2021-01-20
Controller identified | BOF | 400 | 2021-03-11
Approval of event officials | BOF | 400 | 2021-03-11
Safety Officer appointed | Organiser | 200 | 2021-09-27
Webmaster appointed and admin rights granted | Organiser | 200 | 2021-09-27
Entries officer appointed | Organiser | 200 | 2021-09-27
Equipment officer appointed | Organiser | 200 | 2021-09-27
Finance officer appointed | Organiser | 200 | 2021-09-27
Parking team leader/club | Organiser | 200 | 2021-09-27
Starts team leader/club | Organiser | 140 | 2021-11-26
Road crossings team leader/club | Organiser | 140 | 2021-11-26
Enquiries team leader/club | Organiser | 140 | 2021-11-26
Download, results and prize giving team leader/club | Organiser | 140 | 2021-11-26
String course provision | Organiser | 140 | 2021-11-26
Arena management team leader/club | Organiser | 140 | 2021-11-26
Safety and risk management
1st Draft BOF Risk assessments completed | Organiser | 230 | 2021-08-28
Risk assessment approved by Planners, Safety Officer and Controller | Organiser | 220 | 2021-09-07
Issue first aid tenders | Organiser | 210 | 2021-09-17
Finalise contract for first aid cover | Organiser | 180 | 2021-10-17
Ascertain SAG contact position for the area | Organiser | 300 | 2021-06-19
Commence liaison with SAG | Organiser | 250 | 2021-08-08
SAG approval | Organiser | 200 | 2021-09-27
Police notified of road crossing (unless done through SAG) | Organiser | 90 | 2022-01-15
Safety management, missing competitor, first aid detailed plans | Organiser | 90 | 2022-01-15
Notices out for the public, | Organiser | 45 | 2022-03-01
Communicated event with other users of the area | Organiser | 45 | 2022-03-01
Periodic review of risk assessment/updating | Organiser | 30 | 2022-03-16
Mapping
Plan for map update prepared | Organiser | 400 | 2021-03-11
Mapping invitation to participate in tenders sent | Organiser | 400 | 2021-03-11
Mapping tenders issued | Organiser | 390 | 2021-03-21
Mapping tenders received | Organiser | 375 | 2021-04-05
Contract finalised with chosen mapping provider | Organiser | 360 | 2021-04-20
First version of updated map completed | Planners | 270 | 2021-07-19
Supply mappers with map template | BOF | 200 | 2021-09-27
Known areas of map updating to be sent to the mapper | Planners | 150 | 2021-11-16
Map sent to planners and Controller | Planners | 60 | 2022-02-14
Map changes notified to mapper following course setting | Planners | 50 | 2022-02-24
Final mapping visit commences | Planners | 45 | 2022-03-01
Final map updates received from mapper | Planners | 35 | 2022-03-11
Course completion and sign off
Draft courses prepared by planners | Planners | 100 | 2022-01-05
Sites tagged | Planners | 90 | 2022-01-15
Sent to Controller | Planners | 90 | 2022-01-15
Liaise with radio controls team | Planners | 100 | 2022-01-05
Course revisions/discussion with Controller | Planners | 70 | 2022-02-04
Final Controller agreement on courses/sites etc | Planners/C | 30 | 2022-03-16
Final Controller agreement of updated map | Planners/C | 30 | 2022-03-16
Map template layout information agreed | Planners | 30 | 2022-03-16
Finalise course OCAD files with Controller | Planners | 30 | 2022-03-16
Finances, entries and results
Entry system and results tenders issued | Organiser | 220 | 2021-09-07
Draft budget and entry fees agreed with BOF | Organiser | 210 | 2021-09-17
Entry system and results arrangements finalised | Organiser | 190 | 2021-10-07
Obtain photos for flyer | Organiser | 190 | 2021-10-07
Marketing and promotional plan prepared | Organiser | 160 | 2021-11-06
Provide words and pictures for the flyer | Organiser | 150 | 2021-11-16
Flyer 1st draft developed | Organiser | 145 | 2021-11-21
Flyer approved by Planners and Controller | Organiser | 140 | 2021-11-26
Entries information drafted for website | Organiser | 135 | 2021-12-01
Entries information added to website | Organiser | 130 | 2021-12-06
Arrange printing of flyers | Organiser | 130 | 2021-12-06
Flyer distribution | Organiser | 130 | 2021-12-06
Opening date for entries | Organiser | 130 | 2021-12-06
Identify bib provider | Organiser | 130 | 2021-12-06
Provide sponsor logos | Organiser | 80 | 2022-01-25
Notify bib provider of requirements | Organiser | 50 | 2022-02-24
Standard entry closing date | Organiser | 23 | 2022-03-23
Postal entries added | Organiser | 22 | 2022-03-24
Matrix for maps tied to entries | Organiser | 22 | 2022-03-24
Liaise with seeding coordinator | Organiser | 20 | 2022-03-26
Liaise with Commentary team | Organiser | 20 | 2022-03-26
Further liaison with radio controls team | Organiser | 20 | 2022-03-26
Seeding completed by seeding coordinator | Organiser | 20 | 2022-03-26
Late entry closing date | Organiser | 12 | 2022-04-03
Start times posted on website | Organiser | 12 | 2022-04-03
Appoint jury | Organiser | 12 | 2022-04-03
Map printing
Map size and estimated map numbers | Planners | 60 | 2022-02-14
Communication with printer about who to send maps to | Planners | 30 | 2022-03-16
Courses to printers | Planners | 30 | 2022-03-16
Digital proofs received from printers | Planners | 27 | 2022-03-19
Digital proofs checked | Planners/C | 26 | 2022-03-20
Notification of any corrections to printer | Planners | 25 | 2022-03-21
Second digital proofs from printer (if necessary) | Planners | 22 | 2022-03-24
Checking of second digital proofs (if necessary) | Planners/C | 21 | 2022-03-25
Print clearance and final map numbers agreed | Planners/C | 20 | 2022-03-26
Completion of print of blank maps and overprinting/trimming | Printer | 11 | 2022-04-04
Receipt of printed maps and loose control descriptions | Planners/C | 9 | 2022-04-06
Printed maps/descriptions checked | Planners/C | 7 | 2022-04-08
Errors notified to printers (if necessary) | Planners | 5 | 2022-04-10
Corrected maps/descriptions received from printers (if necessary) | Planners/C | 3 | 2022-04-12
String/tag course
Identify area for string course | Organiser | 90 | 2022-01-15
Land access permission obtained for string course area | Organiser | 90 | 2022-01-15
Prepare string course map | Organiser | 60 | 2022-02-14
Arrange printing of string course maps | Organiser | 20 | 2022-03-26
Website/Event Programme
Local information drafted | Organiser | 120 | 2021-12-16
Logo provided | BOF | 120 | 2021-12-16
Check with Highways Authority re road works | Organiser | 60 | 2022-02-14
Draft event programme including arena map and travel directions | Organiser | 60 | 2022-02-14
Clear with planners | Organiser | 50 | 2022-02-24
Clear with Controller | Organiser | 45 | 2022-03-01
Posted to website | Organiser | 40 | 2022-03-06
Prizegiving
Determine location of prize giving in Arena | Organiser | 150 | 2021-11-16
Event prize schedule prepared | Organiser | 100 | 2022-01-05
Recall reminder for trophies | BOF | 100 | 2022-01-05
Equipment
Equipment needs determined | Organiser | 180 | 2021-10-17
Sourcing of forest equipment identified including control nos | Organiser | 160 | 2021-11-06
Decide whether to use a finish gantry | Organiser | 160 | 2021-11-06
Marquee sourcing determined | Organiser | 130 | 2021-12-06
Sourcing of public address, gantry, van hire, trackway, barriers, fencing | Organiser | 130 | 2021-12-06
Sourcing of medals, merchandise as prizes | Organiser | 130 | 2021-12-06
Generator sourcing (with Amplified Sound contract) | Organiser | 130 | 2021-12-06
Monitor roadway improvements | Organiser | 60 | 2022-02-14
Ascertain start clock synchronisation requirements with results | Organiser | 60 | 2022-02-14
Determine all signage needs and arrange their preparation | Organiser | 100 | 2022-01-05
Sourcing of all other equipment identified | Organiser | 60 | 2022-02-14
Security for equipment left on site overnight (professional?) | Organiser | 60 | 2022-02-14
Manpower
Helpers requirements identified | Organiser | 100 | 2022-01-05
People contacted | Organiser | 60 | 2022-02-14
Prepare helper vouchers | Organiser | 60 | 2022-02-14
Email to set out everyone's allocation and timings | Organiser | 7 | 2022-04-08
The unknowns
Consider “What If” scenarios and arranging sourcing of extra needs | Organiser | 21 | 2022-03-25
THREE WEEKS BEFORE
All local residents notified of the event | Organiser | 21 | 2022-03-25
Notify bib provider of bib requirements | Organiser | 21 | 2022-03-25
WITHIN THE WEEK BEFORE
Reconfirm the tractor | Organiser | 6 | 2022-04-09
Roadway and footpath enhancement/cones/grit/brush for entrance | Organiser | 6 | 2022-04-09
Marquee etc reconfirmation | Organiser | 6 | 2022-04-09
Toilet delivery coordination | Organiser | 6 | 2022-04-09
Security company reconfirmation | Organiser | 6 | 2022-04-09
Receive bibs and check all OK | Organiser | 5 | 2022-04-10
Confirm all gate openings/fence crossings in parking/arena/route to S&F | Organiser | 5 | 2022-04-10
Check all gate openings/fence crossings in forest | Planners | 5 | 2022-04-10
Collection/synchronisation of SI equipment | Planners | 6 | 2022-04-09
Check all signs and notices for the event | Organiser | 6 | 2022-04-09
Mark out the arena layout on the ground | Organiser | 6 | 2022-04-09
Check arrangements with the car park, Arena land owners | Organiser | 6 | 2022-04-09
LAST TWO DAYS BEFORE
Collect kit from Matlock | Organiser | 3 | 2022-04-12
Collect kit from other clubs | Organiser | 6 | 2022-04-09
Marquee, tables etc arrive | Organiser | 1 | 2022-04-14
Traders - final confirmation of arrival time/location | Organiser | 3 | 2022-04-12
Safety check | Planners | 3 | 2022-04-12
Put out kites and staves | Planners | 1 | 2022-04-14
Controller to check | Controller | 1 | 2022-04-14
Collection/synchronisation of start clocks | Organiser | 2 | 2022-04-13
Float for Enquiries | Organiser | 1 | 2022-04-14
Clear track from road to parking and path from parking to Arena | Organiser | 1 | 2022-04-14
Prepare bibs for self collection, dibbers for hire and all paperwork | Organiser | 2 | 2022-04-13
Remove fence for Elite start | Organiser | 1 | 2022-04-14
Remove gate near last control | Organiser | 1 | 2022-04-14
Put out all staves for fencing and start | Organiser | 1 | 2022-04-14
Put out as many signs and tapes as practical given the weather | Organiser | 1 | 2022-04-14
Toilets arrive | Organiser | 1 | 2022-04-14
Erect download and enquiries marquees | Organiser | 1 | 2022-04-14
Overnight security arrives | Organiser | 1 | 2022-04-14
ON THE DAY
Unlock toilets | Organiser |  | 2022-04-15
Put out road signs | Organiser |  | 2022-04-15
Put out runners crossing signs | Organiser |  | 2022-04-15
Put out remainder of SI units | Planners |  | 2022-04-15
Start and finish set up and routes to and from | Organiser |  | 2022-04-15
Erect finish gantry | Organiser |  | 2022-04-15
Results display | Organiser |  | 2022-04-15
Brief enquiries about returned trophies | Organiser |  | 2022-04-15
Coordination of traders and first aid siting | Organiser |  | 2022-04-15
Check if gate to cafe is locked or on the latch | Organiser |  | 2022-04-15
Set up prize giving podium | Organiser |  | 2022-04-15
Controllers comments received | Organiser |  | 2022-04-15
Planners and organisers comments | Organiser |  | 2022-04-15
Provisional results and comments to website | Organiser |  | 2022-04-15
Collection of marquees and toilets | Organiser |  | 2022-04-15
AFTER THE DAY
Return kit to other clubs | Organiser
Return kit to Matlock | Organiser
Par times to website | Organiser
Monies banked and event finance summary sent to BOF | Organiser
BOF share of outturn paid | Organiser
Landowners thanked | Organiser
Equipment returned | Organiser
Results finalised | Organiser
Ranking list submitted | Organiser
Post event survey | Organiser
Post event article | Organiser
Event debrief/lessons learned | Organiser
Attend major Events Conference | Organiser
Formulas:
Done By = D3-[Days Before]

## Map printing
| Event date |  | Event date | 2016-06-12
Map printing
Map size and estimated map numbers |  | Planners | 60 | 2016-04-13
Courses to printers |  | Planners | 30 | 2016-05-13
Digital proofs received from printers |  | Planners | 27 | 2016-05-16
Digital proofs checked |  | Planners/C | 26 | 2016-05-17
Notification of any corrections to printer |  | Planners | 25 | 2016-05-18
Second digital proofs from printer (if necessary) |  | Planners | 22 | 2016-05-21
Checking of second digital proofs (if necessary) |  | Planners/C | 21 | 2016-05-22
Print clearance and final map numbers agreed |  | Planners/C | 20 | 2016-05-23
Completion of print of blank maps and overprinting/trimming |  | Printer | 11 | 2016-06-01
Receipt of printed maps and loose control descriptions |  | Planners/C | 9 | 2016-06-03
Printed maps/descriptions checked |  | Planners/C | 7 | 2016-06-05
Errors notified to printers (if necessary) |  | Planners | 5 | 2016-06-07
Corrected maps/descriptions received from printers (if necessary) |  | Planners/C | 3 | 2016-06-09