## PRIZES TEAM
To cfm the eqpt need for prizegiving at JK19 (Days 2, 3 and 4 only):
Transport to move all eqpt (including trophies and medals) between days.
A wheelbarrow to transport trophies (unless the vehicle can drive right up to Enquiries on Days 1 and 2, and right up to the prizegiving tent).
A radio microphone (Helen Errington hoping to include in commentator's contract, please confirm). Following site visits this should not be required but would be good as a fall back option.
Podium - apparently BOF has this. Can you liaise with BOF to obtain this?
Flags to place behind podium. I will liase with clubs if you will ask for 2 from BOF when you speak re podium.
One large and one small tent. Only the small tent is reqd on Day 2 as there are no trophies to award. The Day 3 Arena Manager is providing the large tent that day.
10 trestle tables and 4 chairs. Less will probably be reqd on Day 2 as there are no trophies to award.
Plenty of tape and stakes to cordon off the prize giving area and corral the 100+ recipients.
6 trays to carry medals on. Approx 15x6 inches. Could simply be pieces of wood.

## START TEAM
EQUIPMENT LIST |  | NUMBER | Katy amend
Routes to starts
| Have you got your bib, emit, whistle, waterproof top (at arena exit) | 2
| Compulsory - Full Torso Cover, Whistle, Waterproof top (at arena exit/entrance) | 3
| Sample control on stake (at arena exit) | 1
| Signs to start showing distance, numbers dependant upon distance to start. | 1
| Stakes for signs | various
Start for all three
| Start banner | 1
| Start clock on stand set to real time with beep | 1
| Call up clock on stand set to +5 mins | 1
| Backup digital clock or helpers mobile phones | 1
| Call-up Start lists | 2
Sprint only | List of courses | 1
| Signs for -2, -3, -4- -5 | 1
| Tape for start boxes 500m | 1
| Tape for OOB areas 500m if required | 1
| OOB notices if required | 2
| Tape strips to mark route to first control if required | 1
| Plastic stakes for start to provide high level tape prior to entering the start | 10
| Tent pegs/large headed nails for start box tape | 25
| Map boxes 1-32 depending upon No. of courses. Some to be A3 | 30 | 32 Day 3
| Safety/Final Instructions Notice if required | various
| Maps up to 30 sets | 30 | 32 Day 3
| Up to 30 sets of control descriptions | 30 | 32 Day 3
| Start kite | 1
| Tables for control descriptions | 2 to 4
| Canopies | 2019-04-02
| Pens/pencils/highlighters/notebook | Various
| Waterproof pen for writing on race bibs | 1
| Radio controls | 3
| Clear stations | 1 to 2
| Check Stations | 1 to 3
| Small First Aid Kit | 1
| Bin bags for rubbish | 6
| Hi Vis Jackets, numbers dependant on number of helpers | 7
| Quiet please sign | 2
| Spare e-tags | 10
Sprint only | Start units | 6

## TEMPO_TRAIL
Changes from v1.0 highlighted
TempO - Day 1 |  |  |  | PreO - Day 2 |  |  |  |  | Source
Ser | Use | Item | Quantity | Ser | Use | Item | Quantity | Total Reqt | CBG | GBR TrailO | JK19 | Other
1.1 | FootO Event Centre (EC) | Sign: "TrailO EoD Entry" | x1 |  |  |  |  | x1 |  |  | X
1.2 | FootO Event Centre (EC) | Bibs for EoD entry | x20 | 2 | TrailO Event Centre (EC) | Bibs for EoD entry | x20 | x40 |  |  | X
1.3 | Route to TrailO EC | A3 Sign: "TrailO" | x6 | 2.1 | Route to TrailO EC | A3 Sign: "TrailO" | x6 | x6 |  |  | X
1.4 | Route to TrailO EC | Sign Arrow: Straight on | x5 | 2.2 | Route to TrailO EC | Sign Arrow: Straight on | x6 | x6 |  |  | X
1.5 | Route to TrailO EC | Sign Arrow: Right | x1 | 2.3 | Route to TrailO EC | Sign Arrow: Right | x4 | x4 |  |  | X
1.6 | Route to TrailO EC | Sign Arrow: Left | x4 | 2.4 | Route to TrailO EC | Sign Arrow: Left | x2 | x4 |  |  | X
1.7 | Route to TrailO EC | Cable Ties (Releasable) | x50 | 2.5 | Route to TrailO EC | Cable Ties (Releasable) | tbc | x50 |  |  | X
1.8 | Route to TrailO EC | Tape Route Marking | x1 Roll | 2.6 | Route to TrailO EC | Tape Route Marking | x1 Roll | x2 |  |  | X
1.9 | Disabled Car Park | A2 Sign: "Para Car Park" | x1 | 2.7 | Disabled Car Park | A2 Sign: "Para Car Park" | x1 | x1 |  |  | X
1.9a | Disabled Car Park | Car Park Sign Stake | x1 | 2.7a | Disabled Car Park | Car Park Sign Stake | x1 | x1 | X
|  |  |  | 2.8 | TrailO Event Centre (EC) | Tent - Large | x1 | x1 | X |  |  | Army 12x12?
1.10 | TrailO Event Centre (EC) | Sign: "Registration" | x1 | 2.9 | TrailO Event Centre (EC) | Sign: "Registration" | x1 | x1 |  | X
1.11 | TrailO Event Centre (EC) | Tables | x2 |  |  |  |  | - |  |  |  | On site
1.12 | TrailO Event Centre (EC) | Chairs | x4 |  |  |  |  | - |  |  |  | On site
|  |  |  | 2.7 | TrailO Event Centre (EC) | Tables 6' | x2 | x2 |  |  | X
|  |  |  | 2.8 | TrailO Event Centre (EC) | Chairs | x4 | x4 |  | X
1.13 | TrailO Event Centre (EC) | Results Laptop | x1 | 2.9 | TrailO Event Centre (EC) | Results Laptop | x1 | x1 | X
1.14 | TrailO Event Centre (EC) | Reserve Laptop | x1 | 2.10 | TrailO Event Centre (EC) | Reserve Laptop | x1 | x1 |  |  |  | Other Trail Oers?
1.15 | TrailO Event Centre (EC) | Results Printer | x1 | 2.11 | TrailO Event Centre (EC) | Results Printer | x1 | x1 | X
1.16 | TrailO Event Centre (EC) | Reserve Printer | x1 | 2.12 | TrailO Event Centre (EC) | Reserve Printer | x1 | x1 |  |  |  | Other Trail Oers?
1.17 | TrailO Event Centre (EC) | Power Supply | x1 |  |  |  |  | - |  |  |  | On site
|  |  |  | 2.13 | TrailO Event Centre (EC) | Generator | x1 | x1 |  |  | X
1.18 | TrailO Event Centre (EC) | Results Screen | x1 | 2.14 | TrailO Event Centre (EC) | Results Screen | x1 | x1 | X
1.19 | TrailO Event Centre (EC) | Stationery | various | 2.15 | TrailO Event Centre (EC) | Stationery | various | tbc | X
1.20 | TrailO Event Centre (EC) | A4 Paper | x1 | 2.16 | TrailO Event Centre (EC) | A4 Paper | x1 | x1 | X
1.21 | TrailO Event Centre (EC) | Toilets | x2 |  |  |  |  | - |  |  |  | On site
|  |  |  | 2.17 | TrailO Event Centre (EC) | Portaloo Toilets | x2 | x2 |  |  | X
1.22 | TrailO Event Centre (EC) | Disabled Toilet | x1 |  |  |  |  | - |  |  |  | On site
|  |  |  | 2.18 | TrailO Event Centre (EC) | Disabled Portaloo | x1 | x1 |  |  | X
|  |  |  | 2.19 | TrailO Event Centre (EC) | Water Jerrycan | x1 | x1 |  |  | X | Axel?
|  |  |  | 2.20 | TrailO Event Centre (EC) | Cups & Squash | x100 | x100 | X
|  |  |  | 2.21 | TrailO Event Centre (EC) | EMITags (EoD only) | x40 | x40 | X
|  |  |  | 2.22 | TrailO Event Centre (EC) | EMIT Reader & Printer | x1 | x1 |  |  | X
1.23 | TrailO Event Centre (EC) | TempO Control Cards (A5 W/proof) | x100 |  |  |  |  | x100 |  |  | X | Print Contract
|  |  |  | 2.23 | TrailO Event Centre (EC) | PreO Control Cards (A4 W/proof) | x100 | x100 |  |  | X | Print Contract
1.24 | Course | Direction signs | tbc | 2.24 | Course | Direction signs | tbc | tbc |  | X
1.23 | Course | Tape | x1 | 2.25 | Course | Tape | x1 | x2 |  |  | X
1.24 | Course | Signs: "TempO Stop" | x6 |  |  |  |  | x6 |  | x5 | x1
|  |  |  | 2.26 | Course | Signs: "Stop, Wait" | x2 | x2 |  |  | X
1.25 | Course | Chairs | x6 | 2.27 | Course | Chairs | x2 | x6 |  | X
1.26 | Course | Clipboards | x12 | 2.28 | Course | Clipboards | x4 | x12 |  | X
1.27 | Course | Stopwatches | x12 | 2.29 | Course | Stopwatches | x4 | x12 |  | X
1.27a | Course | Spare Stopwatches | x2 | 2.29 | Course | Spare Stopwatches | x1 | x2 | X
1.28 | Course | Elite Maps: 6 stations x 6 tasks (laminated A5) | 2 sets |  |  |  |  | x72 |  |  | X | Print Contract
1.28a | Course | Standard Maps: 6 stations x 4 tasks (laminated A5) | 2 sets |  |  |  |  | x48 |  |  | X | Print Contract
1.29 | Course | Solution Maps (Plain) | x100 |  |  |  |  | x100 |  |  | X | Print Contract
|  |  |  | 2.30 | Course | Elite Maps (W/proof) | x100 | x100 |  |  | X | Print Contract
|  |  |  | 2.31 | Course | Standard Maps (Plain) | x60 | x60 |  |  | X | Print Contract
|  |  |  | 2.32 | Course | Elite Solution Maps (Plain) | x100 | x100 |  |  | X | Print Contract
|  |  |  | 2.33 | Course | Std Solution Maps (Plain) | x60 | x60 |  |  | X | Print Contract
|  |  |  | 2.34 | Course | Timed Task Maps (2 x 5) (laminated A5) | 2 sets | x20 |  |  | X | Print Contract
1.30 | Course | Umbrellas (Escorts) | x6 | 2.35 | Course | Umbrellas (Escorts) | x2 | x6 | X |  |  | Sports Direct (£18)
1.31 | Course | Spray Paint Soluble | x1 |  |  |  |  | x1 | X |  |  | To be purchased
1.32 | Course | Flags & Canes | x36 | 2.36 | Course | Flags & Canes | tbc | tbc |  | X
|  |  |  | 2.37 | Course | Viewing Pt Numbers (got: Elite 1-20; Std 1-16) | tbc | tbc |  | X
|  |  |  | 2.38 | Course | Viewing Pt Flags (got x25) | tbc | tbc |  | X
|  |  |  | 2.39 | Course | Flag Site Tubing | tbc | tbc |  | X
1.33 |  |  |  | 2.4 | Course | Viewing Pt Tape | x1 | x1 |  | X
1.34 |  |  |  | 2.41 | Course | Skewers/Large Nails | tbc | tbc |  | X
1.35 |  |  |  | 2.42 | Course | Pin Punches (got min 25) | tbc | tbc |  | X
1.36 |  |  |  | 2.43 | Course | Cane Toppers | tbc | tbc |  | X
1.37 | Course | Signs: "Out of Bounds" | tbc | 2.44 | Course | Signs: "Out of Bounds" | tbc | tbc |  | X
|  |  |  | 2.45 | Course | Sign: "TailO Start" | x1 | x1 |  | X
|  |  |  | 2.46 | Course | Flag/Banner: "Finish" | x1 | x1 |  | X
1.38 | TrailO Event Centre (EC) | Start Order Raffle Tickets | 1 set | 2.47 | TrailO Event Centre (EC) | Start Order Raffle Tickets | 1 set | 1 set | X
1.39 | Course/Start | Start Flip 'Clock' | x1 | 2.48 | Course/Start | Start Flip 'Clock' | x1 | x1 |  |  | X | or BAOC?
1.4 | Prizegiving | JK19 Medals: Open & Junior | x6 | 2.5 | Prizegiving | JK19 Medals: Elite; Para; Junior | x9 | x15 |  |  | X | Gold, Silver, Bronze x 5 each
|  |  |  | 2.51 | Course | EMIT TF Start Control | x1 | x1 |  |  | X
|  |  |  | 2.52 | Course | EMIT TF Finish Control | x1 | x1 |  |  | X
1.41 | Course | Correx Board, c 60x15cm, printed with letters "A B C D E F Z" from left to right | x7 |  |  |  |  | x7 |  |  | X
|  |  |  | 2.53 | Course | Correx Board, c 45x15cm, printed with letters "A B C D E" from left to right | x2 | x2 |  |  | X
The main requirements that I need are:
Signs (various) is someone centrally procuring these?
Are we getting JK19 stickers/decals so that signs can easily be re-used in future?
Tape x4 rolls
6’ Tables x2 Day 2 only
Generator Day 2 only
Portaloos Day 2 only (I’ll check with Di who is ordering these)
Watercans Day 2 only
‘Start Flip Clock’ the very, very old type of start clock, manually flipped over! BAOC may have one in the store, but so may other clubs.

## DAY 1
DAY | 1
LOCATION | Aldershot
POC
ITEM | QTY | POOL / CONTRACT | CLUB or BO | HIRE/BUY | COST | REMARKS
JK19 Day 1 Equipment List |  | As at 19 Nov 18
Marquees: |  | Totals:
Download & First Aid | 1
Enquiries, Bibs, Merchandise | 1
Tent:
Officials / Spare | 1
String Cse | 1
Start? | 1
Risk Area 1 - Crossing Point:
Metal barriers | 10+
Risk Area 2 - Entrance to Mons Bks
Runner crossing signs | 4
Large cones | 8
Risk Area 3 - Entrance to Normandy Bks
Runner crossing signs | 4
Large cones | 8
JK Branded signs
Signs Plan for Parking and routes
Event Parking Signs | 4
Disabled Parking Signs | 2
Enquiries' signs | 2
Competitors kit store/changing | 2
Model Event' signs | 2
String course' signs | 2
Route to Sprint O signs | 8
Route to TempO signs | 8
Bibs' signs | 2
Elite Bibs' signs | 2
SLOW - Runners Crossing' signs | 4
Download' sign | 4
Results’ signs | 2
Have you downloaded sign | 2
Club Tents' signs | 2
Club Tent drop-off point | 2
No Tents' signs | 2
Traders' signs | 2
OOB signs | 6
Pedestrian O signs:
To 'Enquiries'
To 'Start'
To 'TempO'
Tape and Posts:
Tape walk to Enquiries | 2
Tape walk to start | 2
Tape start lanes | 2
Tape finish field | 2
Traffic cones | 16
Lightweight white posts (parking area) | 60
Lightweight white posts (for finish field) | 60
Lightweight white posts (for start lanes /boxes) | 20
Stationary:
Ball of string | 1
Cloths Pegs x 100 | 100
Stapler x 2 | 2
Marker Pens x 4 | 4
Red & Blue biros x 18 | 18
Pencils x 18 | 18
Harry black tape | 4
Celotape | 2
JK19 branded tape | 6
Furniture:
Tables:
Enquires | 2
Download | 5
Prize Return | 4
JK19 merchandise pickup | 4
Finish Water Point | 2
Chairs:
Enquires | 4
Download | 6
Misc | 10
Water: WRE MUST - in download / Elites only
Water containers with taps | 3
Paper Cups (recyclable) | 1000
Misc Items:
Finish Arch | 1
Results Boards | 4
High Vis vests | 40
Umbrellas for officials | 10
Clip boards / all weather clip boards) | 10
String Course
SARUM O club to provide
Start Area:
See separate list
Enquires:
Map collection sign
Rope for map collection
Bags for map collection | 50
Results display boards(wood)
Results display boards(plastic) 1.5m x 0.7m
Paste pot and brush
Boxes for car keys, dibbers
Duct tape
Cable ties short
Cable ties long
Whiteboard
Pens
Permanent markers
String for bibs
AA battery for megaphone
Bibs
Safety pins
Cash box
Key Officials Jackets
Volunteer vouchers
Radio
Bin bags
Union Jack
Shovel
Signing plan | etag and bib handout plan?
Major Route signs:
- Main Parking Large 10 x Left turn
- Main Parking Large 5 x Right turn
- Main Parking Large x 4 Straight on
- Helpers Parking 3 x Left turn
- Helpers Parking 2 x Right turn
- TempO Disabled Parking x 2 Left turn
- TempO Disabled Parking x 2 Right turn
- Large Warning Pedestrians x 5
Assembly:
- Left turn x 2
- Right turn x 2
- Straight x 5
Route to Start Signs:
- Left turn x 3
- Right turn x 3
- Straight x 6
Route to TempO from Arena:
- Left turn x 2
- Right turn x 2
- Straight x 9
Parking:
- Coaches here
- Campervans here
TempO disabled Parking
- Left turn x 2
- Right turn x 2
- Straight x 4
Courses
Emit Controls 100-199 | 100
Emit Start controls | 2
Emit Finish controls | 3
Stakes for controls | 110
Kites | 110
Trestles/stands for controls | 30
Black/yellow tape | 50m
Red/white tape | 500m
Stakes for tapes | 50

## DAY 2
DAY | 2
LOCATION | Windmill Hill
POC
ITEM | QTY | POOL / CONTRACT | SOURCE | HIRE/BUY | COST | REMARKS
Course Eqpt | [6 empty] | Who | When
120 stakes for EMIT controls | 120 |  | Club |  |  |  | Pete | 1 week before
No Public Entry. Orienteers only' large signs | 8 |  |  |  |  | updated 17Mar | Pete | 1 week before
3 rolls Black/Yellow tape | 3 |  | Pool |  |  |  | Pete | 1 week before
1 roll red/white tape | 1 |  | Pool |  |  |  | Pete | 1 week before
120 controls | 120 |  | Contract |  | N/A | EMIT | Pete | 1 week before
Emit tags for controller, planner and those putting out controls | 5 | [5 empty] | Pete | 1 week before
120 'clips' to attach stakes to Emit controls | 120 |  | Contract |  | N/A | EMIT | Pete | 1 week before
Arena and admin kit
Tape Run in/OOB area | 2km
Barriers for main run in | 160m |  |  |  |  | Hard standing barriers for the run in 2.3m see https://www.safesitefacilities.co.uk/products/crowd-control-barriers/2-3m-pedestrian-barrier
Finish banner | 1
Stakes (white for tape) | 50 |  |  |  |  | Plastic elec fence type?
Marquee (complete with table and chairs) | 1 off |  | Contract | Hire |  | All Events
Rubbish bags - good quality | 30 off |  | Pool
SN Generator + power block | 1 off |  | Club
Laminator | 1 off
Sheets for lamination | 50 off
Toilet rolls | lots !
Elite Drinks area - Table | 1
Yellow Marshall gilets | 50
Cable Tie wraps | 50
Mallet | 2
wire cutters | 2
Radios | n off |  |  |  |  | (not sure what arrangements made for comms)
Spare tent pegs | 20 off
Results boards
Results boards | 6 off |  |  |  |  | (assume 1 per side of the 2 triangular result boards)
"Results" sign | 2 off
Paste bucket and brushes | 2 off
Prizegiving
Tents for prizegiving | 2 off
Table for prize giving | 2 off
Signage
OOB signs | 10
General direction arrows | 10 |  |  |  |  | For in and around the assembly area
"First aid" sign | 1
"Toilets" sign | 2
"Enquiries" sign | 2
"String course" sign | 1
"Exit" sign | 2
"No entry" sign | 1
Sign - 400m | 1 |  |  |  |  | Park and Pre Park
Sign - 200m | 1 |  |  |  |  | Park and Pre Park
Sign - 100m | 1 |  |  |  |  | Park and Pre Park
Signs - Direction arrows | 8 |  |  |  |  | Park and Pre Park
Sign - NO RIGHT TURN | 1 |  |  |  |  | Park and Pre Park
Sign - TURN AT ROUNDABOUT | 1 |  |  |  |  | Park and Pre Park
Sign/Something for car park marshalls to hold to direct cars from a distance | 6 |  |  |  |  | Park and Pre Park
Sign - TO ELITE START | 2 |  |  |  |  | Starts
Sign - TO START (NOT ELITE) | 2 |  |  |  |  | Starts
Sign - Direction arrow | 2 |  |  |  |  | Starts
Streamers on pegs | 2 |  |  |  |  | Starts
"Caution runners crossing " sign | 2 |  |  |  |  | Starts
"Caution runners on road" sign | 2 |  |  |  |  | Starts
String Course
String course Tent | 1
Table for string course + chair | 1
String | 1 of >1.5km string
Equipment for Individual Day Start Area
General Equipment | Qty |  |  |  |  | Notes
Gazebos (circa 2m x 2m) | 5 |  |  |  |  | One at entry point to call-up at -5; four to cover map tables at -1
Loose description mounting boards/racks | 5 |  |  |  |  | Up to eight nails/hoops on each at -4 (one for elite, 4 for non-elite)
Small tables | 2 |  |  |  |  | For description sheets to keep them off the ground at -4
Map trays/boxes | 26 |  |  |  |  | All A4 size for Day 2
Boards to fit map boxes with cut-away corners to show map no. | 26 |  |  |  |  | All A4 size for Day 2
Large tables | 4 |  |  |  |  | Each must be large enough to take 8 x A4 map trays (4 on each side)
Start banner | 2 |  |  |  |  | Only a small banner needed for separate elite entry point
Shelter tent for helper kit/clothing (Quechua pod, Khyam or similar) | 1
Yellow Tabards for helper team | 20 |  |  |  |  | Enough for everyone on duty, including floating helpers
Red/white tape | 750m
Plastic fence post stakes | 50 |  |  |  |  | For raised tapes where we need to channel competitors, or vertical notices
Reliable pens that will write on waterproof paper when wet | 6 |  |  |  |  | Call-up announcers; emiTag replacers; start line officials (late starters)
Tent pegs | 100 |  |  |  |  | For laying out tape boxes and start lanes on ground
Heavy duty tent pegs (borrow from SN) | 20 |  |  |  |  | Supplementary in case ground is hard or need extra guy lines on gazebos
Spade | 1 |  |  |  |  | To cut small slit trench for e-line at start
Small hammer | 1 |  |  |  |  | For tent pegs
Suggest helpers bring their own chairs/umbrellas if required
Timing Eqpt
Event timing equipment | [5 empty] | Notes
Synchronised bleep clocks (showing seconds) on speaker stands | 2 |  |  |  |  | One at start line; one at non-elite call up (set 5 mins ahead of race time)
Basic bleep clock (digital, showing seconds if possible) | 1 |  |  |  |  | At elite call-up (set 5 mins ahead of race time)
Back up clocks if primary clocks fail | 3 |  |  |  |  | One at start line; two at call-up points
Additional intermediate clocks? | ? |  |  |  |  | Devices showing time at points between call-up and start line
Emit TFP Start station labelled "clear" | 2 |  |  |  |  | One at each call-up
Emit TFP Start station labelled "check" | 1 |  |  |  |  | One at exit of -3 box/entry to -2 start lanes
Emit E-Link transmitter system | 1 |  |  |  |  | Connected to "check" at -2; relays info to computer team
Emit E-Line emiTag detector | 1 |  |  |  |  | Laid in front of map boxes to record who crosses the start line
Spare emiTags | 20? |  |  |  |  | At -5 to issue to anyone whose tag fails to activate
Printed material | Qty |  |  |  |  | Notes
Start lists (all classes in name order) | 2 |  |  |  |  | To display at pre-start before call-up unless already displayed in arena?
Complete start list (start time order) | 1 |  |  |  |  | At -1 to note any late starts
Elite start list (start time order) | 1 |  |  |  |  | At elite call-up, courses 1-4 only
Non-elite start list (start time order) | 2 |  |  |  |  | At non-elite call-up, all except courses 1-4
emiTag exchange record sheet | 2 |  |  |  |  | At each -5 box to record any replaced/substituted tags
Late Starter record sheet | 2 |  |  |  |  | At start line to record actual release times of any late starters
Last minute safety information | 15 |  |  |  |  | Laminated A4; displayed at -3
Start Lane layout | 2 |  |  |  |  | A3 Correx notices? Showing layout of start lanes/course numbers
Map box layouts | 6 |  |  |  |  | Laminated A4; one per start lane at -2 showing map box layouts
Map box labels | 26 |  |  |  |  | Course numbers 1-22 plus W,Y,O,LG (NB. Day 3 needs 1-28 plus CC)
Equipment for Individual Day on the Course
Drinks container | ? |  |  |  |  | Suitable for holding water for 250 competitors - mid race
Table for dispensing drinks | 1
Plastic cups | 250
Note on D4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Club, BO or Outside supplier

## DAY 3
DAY | 3
LOCATION | Cold Ash
POC
ITEM | QTY | POOL / CONTRACT | SOURCE | HIRE/BUY | COST | REMARKS
Arena & Admin kit
Marquee | 1 | Contract | All Events
Tent | 1 | Pool |  |  |  | String Cse
Tape for run in/OOB
Barriers for main run in
Finish Banner
Toilet rolls | think of a number and treble it!
Rubbish bags | 30
Yellow marshall jackets | 50
cable ties
mallets
spare tent pegs
Road Crossing
Tapes for road crossings | Less than 1 reel of red/white
Danger runners crossing signs | Min 6
Signs
Caution Cars Turning | 4
Prize Giving
Large Tent/gazebo | 1 | Steve Waite providing
Small tent | 1 | pool
Water station | 1 (majority of runners, can be visited twice by some)
Table
Water containers
cups and bin bags
Course kit
Controls | See remarks |  |  |  |  | Numbers 70-85, 100-229
Controls | [5 empty] | 3 Start 4 Finish
Kites | 145
Stakes | 145
String course | 13 controls, 1 start 1 finish | 201-213 + S and F | BKO EMIT units 15 stakes/kites
small tent
table and chair
string
Note on D4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Club, BO or Outside supplier

## DAY 4
DAY | 4
LOCATION | Minley
POC
ITEM | QTY | POOL / CONTRACT | SOURCE | HIRE/BUY | COST | REMARKS
GENERAL ITEMS
RED/WHITE TAPE 500m ROLLS | 8
LOTS OF PLASTIC STAKES | [5 empty] | Number to be confirmed after measuring run-in etc
FINISH ARCH | 1
AIR HORN FOR STARTER? | 1 |  |  |  |  | Confirm with Andy MacGregor (Mass Starter)
DOWNLOAD/ENQUIRIES: | [5 empty] | 9x15m
SUITABLE SIZE MARQUEE | 1 |  |  | HIRE |  | in marquee hire charge
TABLES | 8 |  |  | HIRE
CHAIRS | 24 |  |  | HIRE
MAP ISSUE:
TRESTLE TABLES | 3
SMALL TENTS | 2 or 3 |  | TVOC |  |  | TVOC Kyham tents
BOXES FOR MAPS | 6 |  |  |  |  | In Organiser's possession
LARGE RACE TIME DIGITAL CLOCK | 1 | CONTRACT |  |  |  | Timing Team?
EMIT CHECK UNITS (SEVERAL) | 4 | CONTRACT |  |  |  | Timimg Team?
SIGNS FOR ROAD ENTRANCE | [5 empty] | 24"x18" Yellow with black lettering
“TURN LEFT ONLY” | 1 | POOL
“NO RIGHT TURN” | 2 | POOL
LEFT ARROW | 1 | POOL
“ORIENTEERING”SAIL BANNER | 1 | POOL | BO
24"x18" Yellow with black lettering
SIGNS FOR CHANGE-OVER AREA
“MAP ISSUE LEG 1” | 1
LEFT ARROW | 1
UP ARROW | 1
RIGHT ARROW | 1
“MAP ISSUE LEG 2” | 1
"MAP ISSUE LEG 3" | 1
“LEGS 1 AND 2” | 1
“LEG 3 FINISH” | 1
"FINISH" | 1
“MASS START” | 1
“CHANGE OVER” | 1
SIGNS FOR ARENA | 1 |  |  |  |  | 24"x18" Yellow with black lettering
“CLUB TENTS” | 3
SIGNS FOR CAR PARK | 1
"ORIENTEERING THIS WAY" | 3 | POOL | TVOC
“CAR PARK” WITH ARROWS | 1 | Y | TVOC
“CAMPERVANS” WITH AHEAD ARROW | 1
“EXIT” | 1 | Y | TVOC
“CROSSING POINT” |  | Y | TVOC
I WILL MAKE A BIG SIGN FOR MAP ISSUE INDICATING COURSES AND TIMINGS ONCE THESE HAVE BEEN CONFIRMED. I HAVE THE KIT TO DO THIS.
TOILETS:
LOTS NEEDED FOR A RELAY!! + ONE UNIT IN CHANGE-OVER WAITING AREA/OFFICIALS PRIORITY
CONTROLS | Eric Harper
| 100 Controls | CONTRACT
| 100-199 | CONTRACT
| Need duplicates for 100, 101,102 | CONTRACT
| 3 Start | CONTRACT
| 3 Finish | CONTRACT
| 100 Stakes | POOL
| 100 Kites | POOL