## Key actions and Milestones
Multi-day Event |  | Project Action Plan
Key actions and milestones (see subsidiary sheets for detailed action plans under each heading.
KEY ACTIONS AND MILESTONES |  |  |  | 2015 | [5 empty] | 2016 | [5 empty] | 2017 | [5 empty] | 2018
Action |  | Responsible | Finish | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O
Event Date
Key milestones
| Host Association allocated JK | ESG
Partnership Agreement signed
Permissions finalised & land access agreements signed
| JK format finalised | C
Risk Assessments complete
| Apply for IOF WRE status | C, Day O, EP&PG
| IOF Event Advising team populated | IOF
| Merchandising live | MEM
Mapping completed
Event Organisation
Strategic Group Meetings
Organising Group Meetings
Recruit Key Roles in Organising Group
| Controller Appointed | EOG
| Recruit Planning Teams | Day O, C
| Recruit Team Leaders | Day O
| Recruit Team personel | Day O
Event Management
Equipment |  | Equip
Travel and Transport
Safety Advice Group Liaison |  | Safety
Road Signs
Buses
Social Programme |  | WMJS - Tracy Craig
Competiton Management
| Select Areas | Team
| Formalise Access Permissions | Team
Course Planning
Appointment of Planning teams
Planning strategy
Draft Courses
Final Courses
Computing
Results |  | Sportident
Arenas
| Confirm arena venues | C, Day O,MEM
Arena design
Training camps & pre-competitons
Appoint training coordinator/organiser
Produce training and competiton strategy/plan
Indenfity areas for camps and compeittons
Identify organisers for each camp/competition
Mapping
| Define areas to be mapped | Map C
| Send out mapping tender documents | Map C
| Place mapping contracts | Map C
| Place map printing contract | Map C
Marketing & Communications
Marketing and Publicity
Event Name
| Event Logo | MEM, MM, Team
| Produce marketing strategy | MM, MEM
Website
| Website goes live | MEM
Programm/Bulletins
| WRE Bulletin 1-4 months before event | C
| WRE Bulletin 2-1 week before event | C
Information and News Sheet
Commercial
Finance
| Produce draft budget | Fin, MEM, Team
Produce yearly cash flow
Sponsorship
Merchandising |  | MEM
Traders contracts |  | MEM
KEY |  |  |  |  | KEY
Each of above headings includes : |  |  |  |  | Responsibilities - abbreviations
[5 empty] | C |  |  | Coordinator (local)
Event Admin and Finance |  |  |  |  | MEM |  |  | Major Events Manager (BOF)
- Admin |  |  |  |  | AC (local) |  |  | Assistant Coordinator (local)
- Finance |  |  |  |  | Team |  |  | Central Organising Team
- Competitor mailing |  |  |  |  | Fin |  |  | Finance Coordinator
- Results booklet |  |  |  |  | Day O |  |  | Day Organisers
- Debriefing |  |  |  |  | Day P |  |  | Day Planners
- Booking toilets |  |  |  |  | Day Cont |  |  | Day Controllers
- Recycling and Refuse |  |  |  |  | Safety |  |  | Safety Officer
- Group accommodation |  |  |  |  | Ent |  |  | Entries Secretary
[5 empty] | Equip |  |  | Equipment Coordinator
Programme |  |  |  |  | Pub |  |  | Publicity Coordinator
[5 empty] | MM |  |  | Marketing Manager (BOF)
Entries |  |  |  |  | Prog |  |  | Programme editor
[5 empty] | Web |  |  | Website manager
Orienteering |  |  |  |  | TrailO |  |  | TrailO Coordinator
- Areas |  |  |  |  | String C |  |  | String Course coordinator
- Permissions |  |  |  |  | Prizes |  |  | Prize & prize giving Coordinator
- Mapping |  |  |  |  | Map C |  |  | Mapping coordinator
- Planning |  |  |  |  | Tech C |  |  | Technical coordinator
- Controlling |  |  |  |  | Comm |  |  | Commentators
- Day Organisation |  |  |  |  | EOG |  |  | Event Officials Group
- Training |  |  |  |  | EP&PG |  |  | Event Programme & Publicity Group
- String Courses |  |  |  |  | ESG |  |  | Event Scheduling Group
- Rest Day Programme
Mapping
Entries
Marketing and Publicity
- Marketing
- Publicity
- Merchandising
- Press
Web site
Prizes, Certificates and Badges
Equipment
Traders contracts
Sponsorship
Computing
- SI liaison
- Results computing
- Management of appeals and protests
- On the day entries
Results
Event Centre and Campsite
Information and NewsSheet
- Event Centre enquiries
- Assembly enquiries
- Daily newssheet
Travel and Transport
- Police Liaison
- Road Signs
- Buses
Socials
Rest Day Activities

## Admin, Finance
Multi-day Event | Project Action Plan
ACTIONS AND MILESTONES |  |  | 2016 | [5 empty] | 2017 | [5 empty] | 2018
| Responsible | Finish | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O
Event Admin and Finance
Organising Team Meetings
Register event with BOF
Recruit Key Roles in Central Organising Team
Recruit all roles in Central Organising Team
Review reports/feedback from previous JK
List and communicate proposed changes
Seek approval from E&CC for deviation from Rules
Ensure changes immplemented
Complete event Budget
Pay invoices and record expenditure
Monitor and record income
Monitor and update budget
Set entry fees
Decide refunds policy and cut off dates
Chase up outstanding invoices and expenses
Complete post event final accounts | MEM
Disbursement of profit share to association/club
Info emailed or posted to overseas competitors
Info emailed or posted to UK competitors (not at home in July)
Main Officials debriefing
Toilets
Decide spec. | MEM, C
Obtain quotations | MEM, C
Place contract | MEM
Site visit with supplier | Day O
Monitor implementation | MEM, C, Day O
Recycling/Refuse
Decide spec. - Event sites | MEM, C
Obtain quotations | MEM, C
Place contract | MEM
Monitor implementation | MEM, C, Day O
Accommodation
Set up Guestlink | MEM
Provide info to go on website | MEM, Web

## Programme
Multi-day Event | Project Action Plan
Proposed Timetable for Event Programme | Responsible | Finish | September |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April
|  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3
Draw-up List of Contributors | Prog, C | bar: September 1 to September 2
Agree Timetable for Preparing Copy | Prog, C | bar: September 2 to September 3
Inform Contributors of Process | Prog, C | bar: September 3 to September 4
Agree Content of Contributions | Prog, C | bar: September 4
Day officials & other team leaders to agree arrangements for coordination & submission of copy | Day O, Ent, C | bar: September 4
Preparation of Copy within teams | Day O, Ent, C | bar: October 1 to October 2
Copy to Prog | Day O, Ent, C
Programme Editors chase late Copy & check received Copy | Prog | bar: October 3
Cut-off date for draft copy | Prog | bar: October 4
Send Event Programme v1 to contributors | Prog | bar: November 1
Comments back on Event Programme v1 | Day O, Ent, C | bar: November 1
Event Programme v1 distributed for checking | Prog | bar: November 2
Proof read Event Programme v1 | Prog | bar: November 3
Agree & Publise Event Programme v1 | Prog, Web, Pub | bar: November 3
Update & publise other versions of Event Programme | Prog | on going | bar: December 1 to April 3

## Entries
Multi-day Event | Project Action Plan
ACTIONS AND MILESTONES |  |  | 2016 | [5 empty] | 2017 | [5 empty] | 2018
| Responsible | Finish | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O
ENTRIES
Review previous JK report
Set entry system specification (+ outputs)
Investigate online entry system providers
Propose provider
Decide provider
Place contract with specifications
Design paper entry system
Trail run / test of entry system
On-line entries live
Monitor system operation
Deal with any refund requests
Report at first cut off date
Deal with paper entries and enter data
Final number estimate from entry at first cut off
Report at second cut off date
Plan provision of entry data to computing
Entries close
Specify requirements for start time allocation system
Set up start allocation system
Allocate start times
Ensure all special requests related to start times dealt with
Publish start lists on website
Deal with enquiries and change request after start lists published
Provide data to computing for SI database
Provide data to computing for bibs, labels
Final numbers to mapping coordinator
Deal with any late entries
Plan registration system for EOD
Recruit and train EOD /registration team
Organise EOD/registration rota for event
Oversee operation of EOD system at event
Deal with change requests
Monitor and manage priority parking
Monitor and manage no. of cars, coaches, mini buses, camper vans
Monitor and manage Bus bookings

## Orienteering Training & String
Multi-day Event | Project Action Plan
ACTIONS AND MILESTONES |  |  | 2016 | [5 empty] | 2017 | [5 empty] | 2018
| Responsible | Finish | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O
Orienteering
Select Areas
Formalise Permissions
Confirm Parking and Assembly Areas
Define areas to be mapped
Allocation of clubs to days
Decide details of description hand out at start
Appointment of Controllers | EOG
Appointment of Planners
Prepare Area Info pack, including landowner contact details, access details, constraints and restrictions, sketch maps showing area, assembly, parking for planners, controllers and day organisers
Distribute info packs to planners, controllers, day organisers & Safety Officer
Appointment of Day organisers
Compile and maintain contact list of Day Officials
Prepare and Issue Day Organisers Manual
Update Day Org Manual as necessary
Monitor Day Org progress against timetable in manual
Prepare and Issue Technical Manual
Update Tech Manual as necessary
Monitor Planning and Controlling progress against timetable in manual
Confirm Elite format
Define Condes version to be used and place template on web
Arrange Condes training if needed
Decide if radio controls to be used (all days)
Decide sites for Radio controls
Monitor entry numbers against courses
Assess help needed on each day
Email entrants seeking volunteers for on the day help
Allocate helpers to days
Define requirements for production of description sheets
Arrange production of description sheets with map printing
Description sheets delivered to event centre
TRAINING
Review previous JK Reports
Proposed training programme for JK
Decide training to be provided for JK
Identify training areas
Assess quality of maps of identified areas
Arrange update of maps as necessary
Plan distribution of training packs
Plan training courses
Ensure parking provision at venues
Organise any coaching provision
Prepare training packs
Arrange distribution points for training packs
Liase with Information Team Leader on distribution of training packs at Info point during event
Distribute training packs
Place controls
Monitor availability of packs
Remove controls
STRING COURSES
Review previous JK Reports
Decide String Course parameters for JK
Prepare String Course guidelines
Distribute guidelines to Day Organisers
Arrange provision of string course equipment
Identify String Course Areas
Prepare String Course maps
Monitor planning/organisation of String Courses
Day controllers check and approve string courses
Arrange distribution of string course prizes to each day
Facilitate handing over of String Course equipment from each day to the next day.

## Mapping
Multi-day Event | Project Action Plan
ACTIONS AND MILESTONES |  |  | 2016 | [5 empty] | 2017 | [5 empty] | 2018
| Responsible | Finish | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O
Mapping
Review previous JK mapping and map printing timetable
Decide mapping and map printing timetable
Communicate and agree timetable with Tech coordinator and Coordinator
Define areas to be mapped
Send out mapping tender documents
Place mapping contracts
Place map printing contract
Draft map to planners and controllers
Ensure survey of summer vegetation
Map corrections from planners/controllers
Map corrections to mappers
Design map layouts including logos
Get quotations/tenders for map printing
Place map and description sheet printer contract
Condes file to printer for proofing
First digital proof to planners/controllers
Info on map sizes to programme & website
Comments on first proof to printer
Final digital proof to Planners/Controllers
Controllers approve final digital proofs
Print numbers for each course to printer
Maps printed, copy of each to planners/controllers
Planners & Controllers check paper copy
Any problems notified to Mapping coordinator
Actions taken to rectify view of any problems
Maps delivered to Controller to check

## Marketing and Publicity
Multi-day Event | Project Action Plan
ACTIONS AND MILESTONES |  |  | 2016 | [5 empty] | 2017 | [5 empty] | 2018
| Responsible | Finish | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O
Marketing and Publicity
Event Name
Event Logo
Advert in Focus
Publicity at previous JK
Event Programme Preparation
Decide when to launch Event Programme
Decide Event Programme format (folded A4 or A3)
Design Event Programme
Collect all input to Event Programme
Identify printer for Event Programme
Prepare artwork for Event Programme
Arrange printing of Event Programme
Event Programme Launch
Arrange Brochure distribution at UK events
Arrange Brochure Distribution abroad
Press reports
Article in CompassSport | Team, MEM
Article in Focus (British Orienteering) | Team, MEM
Establish contacts with local and national media | MEM
Press releases to local papers | MEN
Press releases to National papers | MEM
Press releases during the event - results and stories
Post event press releases | MEM
Merchandising
See MEM programme | MEM

## Website
Multi-day Event | Project Action Plan
ACTIONS AND MILESTONES |  |  |  | 2016 | [5 empty] | 2017 | [5 empty] | 2018
| Responsible | Information | Finish | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O
Provider
WEBSITE and RESULTS
Create event website
Event website goes live
Develop website based on previous JK website & Feedback
Add information as available:
Entry fees
Date for entries opening
Cut off dates for low entry fees - with reminders as dates approach
Info on refunds and cut off dates
Info on making changes to entries
Info on postal entries
Info on enquiries
Classes and approx course lengths
Accommodation info
Colour coded course explanation
Info on EOD
Training Programme details
Info an Social activities
Link to entry system
Event Programme posted on website
Start lists
Links to other sites as appropriate
Sponsor adverts and logos
RESULTS on website
Pre-event trial uploading to website
Daily download to website at event
Info on Route Gadget and links on website

## Prizes
Multi-day Event | Project Action Plan
ACTIONS AND MILESTONES |  |  | 2016 | [5 empty] | 2017 | [5 empty] | 2018
| Responsible | Finish | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O
PRIZES and PRIZEGIVING
Use prize giving schedule | MEM, Prize
Get medal design | MEM
Approve medal design & numbers | MEM
Confirm engraving | MEM
Get Buff design | MEM
Approve Buff design & numbers | MEM
Order Elite vouchers | MEM
Decide on main officials momentos | Team
Plan prizegiving order | Prize
Organise delivery &/or getting prizes to event | MEM
Organise people to give prizes | C
Use BOF podium for prizegiving | MEM | at event
Ensure PA system suitable for prizegiving | Day O, MEM
Publicise and manage spot prizes (donated by sponsors) | Comm, Prize | at event
Prizewinners lists from computing | Prize | at event
Run Prizegiving | Prize | at event

## Equipment
Multi-day Event | Project Action Plan
ACTIONS AND MILESTONES |  |  | 2016 | [5 empty] | 2017 | [5 empty] | 2018
| Responsible | Finish | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O
EQUIPMENT
Decide how to organise equipment team
Recruit equipment team members
Info on equipment on BOF website
Collect information on Day needs
Order water for WRE Elite Days
Arrange van/vehicle hire
Check equipment stocks in Clubs/Association
Order any extra equipment needed
Ensure material available for stiles/bridges
Erect stiles and bridges
Deliver equipment to event sites
Deliver water etc to on course drinks points
Deliver maps to starts
Source staging for prizegiving
Position staging for prizegiving
Brief team on roles/ tasks for event
Collect equipment from BOF store | MEM
Deliver BOF equipment to each event site | MEM, Equip
Advise Day teams as necessary on erection of equipment
Load up equipment at end of each day event to transfer to next site | MEM, Equip, Day O
After event, recover equipment, sort and return to store | MEM
Signs
List of signs required in arena, from car park, to starts etc | Day O, Equip
Identify suppliers, design with JK logo and obtain quotes
Place orders
Generators
Decide requirements and specs
Identify suppliers and obtain quotations
Place orders
Deliver to event sites and oversee operation
2-way Radios
Decide requirements and specs | Day O, Equip
Identify suppliers and obtain quotations | MEM, Equip
Organise delivery to event sites and manage issue, return and recharging | Day O, Equip
PA and Radio Controls - see Computing

## Trader Contracts
Multi-day Event | Project Action Plan
ACTIONS AND MILESTONES |  |  | 2016 | [5 empty] | 2017 | [5 empty] | 2018
| Responsible | Finish | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O
TRADERS CONTRACTS
Set Traders fees | MEM
Amend contracts | MEM
Contact Traders | MEM
Deal with any enquiries from Traders | MEM
Determine LA Street Trading licence requirements | MEM
Notify Traders of Street Trading license | MEM
Issue contracts | MEM
Collect copies of licences, certificates, risk assements etc | MEM
Liaise with Day Organisers regarding positioning of traders in Arenas | MEM, Day O
Plan Trader space allocations in Arenas | MEM, Day O
Mark out Trade areas in Arenas | MEM, Day O
Liaise with Traders during event | MEM, Day O

## Sponsorship
Multi-day Event | Project Action Plan
ACTIONS AND MILESTONES |  |  | 2016 | [5 empty] | 2017 | [5 empty] | 2018
| Responsible | Finish | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O
SPONSORSHIP
Agree who will look after Public body sponsorship | MEM or Day Org
Contact potential commercial sponsors
Organising committee to pass any potential sponsors contacts to MEM
Obtain Sponsors logo
Promotion of sponsors on website
Collect banners etc from sponsors to use at the event
Arrange with Day Organisers and Equipment team to display banners at events
Promotion of sponsors at event - banners, commentary
Return banners etc to sponsors after event

## Computing
Multi-day Event | Project Action Plan
ACTIONS AND MILESTONES |  |  | 2016 | [5 empty] | 2017 | [5 empty] | 2018
| Responsible | Finish | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O
COMPUTING
Review previous JK reports
SI Contract
Review SI contract spec
Discuss required contract spec with SI
Obtain quotation from SI
Place SI contract
Entries and start time allocation | see Entries spreadsheet
Ensure competitor data files handed over to SI for SI event database
Print start lists each for day at event
Generate seeding, start times for elite
Bib Printing
Indentify printer | MEM
Obtain bib proof & identify number ranges | MEM
Get quote | MEM
Set schedule: entries closing date, start time allocation, Elite seeding, printing time & delivery | MEM
EOD/Registration | see Entries spreadsheet
Computing (continued)
Orienteering
Enter course/control/class data
Liaise with SI staff during event
Ensure provision of adequate numbers of SI units and SI cards
Oversee initial programming of SI units
Manage collection, reprogramming and handing on of SI units from day to day
Oversee operation of download
Ensure any SI or computing related problems resolved
Radio controls / commentary
Decide if Radio controls to be used
If radio controls ensure entry system captures suitable competitor information (part of entry process)
Organise data to make competitor information, linked to radio control ouput, available to comentary team.
PA equipment and Radio controls
Decide requirements and specs
Identify suppliers and obtain quotations
Place orders
Contract commentator(s)
Organise radio controls and liaise with planners/controllers/commentary team over use
Organise PA delivery to event sites
Oversee PA operation during event

## Results
Multi-day Event | Project Action Plan
ACTIONS AND MILESTONES |  |  | 2016 | [5 empty] | 2017 | [5 empty] | 2018
| Responsible | Finish | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O
Results
Consider possible results display improvements | C, Day O, Equip
Decide results display format for Assembly at events | C, Day O, Equip, MEM
Periodic results printouts at event |  | at event
Liaise with Day organsier to organise results display at each day | MEM, C | at event
Ensure previous day results and start lists displayed each day | Day O | at event
Produce prizewinners list |  | at event

## Information and News
Multi-day Event | Project Action Plan
ACTIONS AND MILESTONES |  |  | 2016 | [5 empty] | 2017 | [5 empty] | 2018
| Responsible | Finish | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O
INFORMATION
Review previous JK Report
Respond to e-mail enquiries via web site
Set up e-mail addresses for enquiries
Ensure enquiries details on web site
Set up postal entries address
Respond to postal enquiries
Prepare forms and paperwork for Entries & Enquiries
Postal entries form
Punching start permit cards
Protest / complaint forms
Recruit team for manning Enquiries at Event
Prepare and issue Rota for manning Enquiries at the Event
Operate registration: bibs and SI cards collection
Organise Enquiries for each day of Event

## Safety, Travel and Transport
Multi-day Event | Project Action Plan
ACTIONS AND MILESTONES |  |  | 2016 | [5 empty] | 2017 | [5 empty] | 2018
| Responsible | Finish | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O
Safety Advisory Group
Identify point of contact with relevant SAG
Regular updates on event to SAG
Communicate with SAG on any issues relating to event which SAG should know about or which require assistance from them
Signs
Review previous JK Report
Seek Local Authority/Hwys advice
Prepare Schedule and travel directions
Check travel directions with SAG & LA/Hwys
Amend schedule after SAG & LA/Hwys input
Confirm specifications for road signs
Check confirmed JK Schedule
Check road sign sites (can use Google Earth)
Assess needs for new lettering and logos (or new signs)
Get quotes for lettering / logos (or signs)
Order lettering / logos
Arrange who will position signs, LA/Hwys guidance
Arrange who will move/collect signs, LA/Hwy guidance
Buses
Review any requirement for bussing
Decide what bussing we will offer at event
Set bus fees
Identify turning/parking space at event venues
Plan timings
Compile Bus schedule and specification
Identify bus suppliers
Obtain quotations
Place contracts
Monitor bus bookings against buses ordered
Liase with Entries on start times for bus passengers
Arrange issue of bus tickets
Oversee bus operation during week