## Key actions and Milestones
Key actions and milestones (see subsidiary sheets for detailed action plans under each heading.
|  |  | Year 1 | [5 empty] | Year 2 | [5 empty] | Year 3
Action | Responsible | Finish | QU1 | QU2 | QU3 | QU4 | S - O | N - D | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O
Event Admin and Finance
Organising Team Meetings
Register event with SOA and BOF
Recruit Key Roles in Central Organising Team
Recruit all roles in Central Organising Team
Complete event Budget
Set entry fees
On-line entries live
Entries close
Programmes, bibs and info posted
Main Officials debriefing
For more details see subsidiary sheet
Entries
Prizes and prizegiving
Orienteering
Select Areas
Formalise Permissions
Confirm Parking and Assembly Areas
Allocation of clubs to days
Appointment of Planners and Controllers
Appointment of Day organisers
Prepare and Issue Day Organisers Manual
Prepare and Issue Technical Manual
For more details see subsidiary sheet
Training
String Courses
Rest Day Programme
Mapping
Define areas to be mapped
Send out mapping tender documents
Place mapping contracts
Place map printing contract
For more details see subsidiary sheet
Event Centre & Campsite
Identify Event Centre and campsite
Agree Event Centre contract
For more details see subsidiary sheet
Marketing and Publicity
Event Name
Event Logo
Advert in 2007 programme
Publicity at Spey 2007
Event website goes live
Event Brochure Preparation
Event Brochure Launch
Event Brochure Distribution abroad
Advertising in overseas magazines starts
Brochures to BOF for mailing
For more details see subsidiary sheet
Programme
Merchandising
Website
Equipment
Traders contracts
Sponsorship
Computing
Results
Information and NewsSheet
Travel and Transport
Police Liaison
Road Signs
Buses
Socials

## Admin, Finance
ACTIONS |  |  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3
| Responsible | Finish | Qu1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4
Event Admin and Finance
Organising Team Meetings
Register event with BOF
Recruit Key Roles in Central Organising Team
Recruit all roles in Central Organising Team
List and communicate proposed changes
Ensure changes immplemented
Complete event Budget
Pay bills, maintain accounts
Monitor and record income
Monitor and update budget
Set entry fees
Decide refunds policy and cut off dates
Chase up outstanding invoices and expenses
Arrange payments to BO
Disbursement of profits to clubs
Main Officials debriefing
Toilets
Decide spec.
Obtain quotations
Place contract
Site visit with provider
Monitor implementation
Recycling/Refuse
Decide spec.
Obtain quotations
Place contract
Monitor implementation

## Final details
ACTIONS | Responsible | Finish | Year 1 |  |  |  | Year 2 |  |  |  | Year 3
|  |  | Qu1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4
Appoint Printer & Agree Copy Date
Draw-up List of Contributors
Agree Timetable for Preparing Copy
Inform Contributors of Process
Agree Content of Contributions
Day officials & other team leaders to agree arrangements for coordination & submission of copy
Preparation of Copy within teams
Copy to Prog. Editors
Programme Editors chase late Copy & check received Copy
Advertising Copy to Prog. Editors
Cut-off date for draft copy
* Send Draft Programme to contributors
* Comments back on Draft Programme
Final Version Distributed for checking
Proof read final copy
Agree Final Copy & Number required
Submit Copy to Printers
Sign off printers proof
Printed Programmes Returned
Envelope Programmes & Post
* In 2009 these two steps were dispensed with for most Programme sections.

## Entries
ACTIONS |  |  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3
| Responsible | Finish | Qu1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4
ENTRIES
Set entry system specification (+ outputs)
Investigate online entry system providers
Propose provider
Decide provider
Place contract with specifications
Design paper entry system
Trail run / test of entry system
On-line entries live
Monitor system operation
Deal with any refund requests
Report at first cut off date
Deal with paper entries and enter data
Final number estimate from entry at first cut off
Report at second cut off date
Plan provision of entry data to computing
Entries close
Specify requirements for start time allocation system
Set up start allocation system
Liasie with ECG and JCG for selection and seeding requirements
Allocate start times
Ensure all special requests related to start times dealt with
Publish start lists on website
Deal with enquiries and change request after start lists published
Provide data to computing for SI database
Provide data to computing for bibs, labels
Final numbers to mapping coordinator
Deal with an late entries
Plan registration system for EOD
Recruit and train EOD /registration team
Organise EOD/reegistration rota for event
Oversee operation of EOD system at event
Deal with change requests

## String course
|  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3
ACTIONS |  | Qu1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4
Responsible
Orienteering
Note - detailed actions of planners and controllers are in Technical Manual
Note - detailed actions of organisers are in Organisers Manual
Select Areas | C, AC
Formalise Permissions | AC
Confirm Parking and Assembly Areas | AC
Define areas to be mapped | AC,C
Allocation of clubs to days | AC,C
Decide details of description hand out at start | Day C
Appointment of Planners and Controllers | Tech C, AC
Prepare Area Info pack, including landowner contact details, access details, constraintsand restrictions, sketch maps showing area, assembly, parking for planners, controllers and day organisers | AC
Distribute info packs to planners, controllers and day organisers | AC
Appointment of Day organisers | Day C, AC
Compile and maintain contact list of Day Officials | AC
Prepare and Issue Day Organisers Manual | Day C
Update Day Org Manual as necessary | Day C
Monitor Day Org progress against timetable in manual | Day C
Prepare and Issue Technical Manual | Tech C
Update Tech Manual as necessary | Tech C
Monitor Planning and Controlling progress against timetable in manual | Tech C
Confirm Elite format | C, AC, Team
Define Condes version to be used and place template on web | Tech C, Web
Arrange Condes training if needed | Tech C
Decide if radio controls to be used (all days) | Team
Decide sites for Radio controls | Tech C, AC
Monitor entry numbers against courses (240 max) | Ent & Tech CDC
Assess help needed on each day from non Scottish clubs | Day C
Email entrants seeking voluntreers for on the day help | Ent, Day C
Allocate non SOA club helpers to days | Day C
Define requirements for production of description sheets | Tech C
Arrange production of description sheets with map printing | Map
Description sheets delivered to event centre | Printer
0 | 0
0
ACTIONS
Responsible
TRAINING
Review Spey 2007 Reports
Proposed training programme for 2009
Decide training to be provided for 2009
Identify training areas
Assess quality of maps of identified areas
Arrange update of maps as necessary
Plan distribution of training packs
Plan training courses
Ensure parking provision at venues
Organise any coaching provision
Prepare training packs
Arrange distribution points for training packs
Liase with Information Team Leader on distribution of training packs at Info point during event
STRING COURSES
Decide if String Course possible
Arrange provision of string course equipment
If electronic equipment used, order & programme & return.
Identify String Course Area
Prepare String Course maps
Controller to check and approve string course
Obtain of string course prizes

## Mapping
ACTIONS AND MILESTONES |  |  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3
| Responsible | Finish | Qu1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4
Mapping
Decide mapping and map printing timetable
Communicate and agree timetable with Map Adviser & Controller & Planner
Define areas to be mapped
Send out mapping tender documents
Place mapping contracts
Place map printing contract
Draft map to planners and controllers
Ensure survey of seasonal vegetation
Map corrections from planners/controllers
Map corrections to mappers
Design map layouts including logos
Get quotations/tenders for map printing
Place map and description sheet printer contract
Overprint file to printer for proofing
First digital proof to planners/controllers
Info on map sizes to programme & web site
Comments on first proof to printer
Final digital proof to Planners/Controllers
Controllers approve final digital proofs
Print numbers for each course to printer
Maps printed, copy of each to planners/controllers
Planners & Controllers check paper copy
Any problems notified to Mapping coordinator
Actions taken to rectify view of any problems

## Marketing and Publicity
ACTIONS |  |  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3
| Responsible | Finish | Qu1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4
Marketing and Publicity
Event Name
Event Logo
Advert at previous years event
Publicity at events
Event Brochure Preparation
Decide when to launch brochure
Decide Brochure format (folded A4 or A3)
Design Brochure
Collect all input to brochure
Identify printer for brochure
Prepare artwork for brochure
Arrange printing of brochure
Event Brochure Launch
Arrange Brochure distribution at UK events
Arrange Brochure Distribution abroad
Advertise in Compassport
Advert in other event programmes
Consider Advertising in overseas magazines
Liaise with BOF about Brochure mailing
Press reports
Article in CompassSport
Article in Focus (British Orienteering)
Establish contacts with local and national media
Press releases to local papers
Press releases to National papers
Press releases during the event - results and stories
Post event press releases
Merchandising if applicable
Decide if wish to have a merchandising range of goods
Decide merchandise budget
Decide if Org Team to have free identifying polo shirt
Investigate on line sales
Implement online sales if chosen route
Design and specifications for merchandise
Identify suppliers for merchandise
Arrange production and delivery of merchandise
Plan sale at event of merchandise
Organise sale of merchandise at event

## Website
ACTIONS |  |  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3
| Responsible | Finish | Qu1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4
WEBSITE and website results
Develop website
Add information as available
Entry fees
Date for entries opening
Cut off dates for low entry fees - with reminders as dates approach
Info on refunds and cut off dates
Info on making changes to entries
Info on postal entries
Classes and approx course lengths
Bus fees and details
Colour coded course explanation
Info on EOD
Link to entry system
Deccide if Officials section of website is required
Updates to Officials section
Programme posted on website
Start lists
Links to other sites as appropriate
Sponsor adverts and logos
RESULTS on website
pre-event trial uploading to website
Info on Route Gadget and links on website

## Trophies, Prizes & Mementos
ACTIONS |  |  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3
| Responsible | Finish | Qu1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4
TROPHIES
Contact Events Managers to commence trophy recall procedure
Provide contact details for previous Trophy holders letter
Chase all previous Trophy holders to ensure all are returned on or before the event
Liaise with Events Managers about any broken or missing trophies.
Take delivery of Trophies at the Event
Ensure list of the correct trophy for each class is ready for Prize Giving
Provide a list of new trophy holders to be supplied to Events Managers
PRIZES and PRIZEGIVING
Contact Events Managers to see what prizes to award
Decide if having helper/main officials mementos
Confirm prizes are suitable
Order prizes/arrange delivery
Decide on Memento and arrange samples
Order Mementos & arrange delivery
Plan prizegiving
Organise people to give prizes
Source staging for prizegiving
Ensure PA system suitable for prizegiving
Publicise and manage spot prizes if applicable
Prizewinners lists from computing
Run Prizegiving
CERTIFICATES if required
Produce certificate template
Print certificates

## Equipment
ACTIONS |  |  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3
| Responsible | Finish | Qu1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4
EQUIPMENT
Decide how to organise equipment team
Recruit equipment team members
Collect information on Day needs
Order water for finish if required
Arrange van/vehicle hire
Check equipment stocks in store
Source any extra equipment needed
Ensure material available for stiles/bridges
Erect stiles and bridges if required
Deliver eqiupment to event sites
Deliver water etc to on course drinks points
Deliver maps to starts
Source staging for prizegiving
Position staging for prizegiving
Brief team on role
Collect equipment from British Orienteering Store
Deliver equipment to event site
Advise Day team as necessary on erection of equipment
After event, recover equipment, sort and return
Generators
Decide requirements and specs
Identify suppiers and obtain quotations
Place orders
Deliver to event sites and oversee operation
2-way Radios
Decide requirements and specs
Procure any radios needed
Organise delivery to event site and manage issue, return and recharging

## Trader Contracts
ACTIONS |  |  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3
| Responsible | Finish | Qu1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4
TRADERS CONTRACTS
Set Traders fees
Amend standard British Orienteering trader contact if necessary
Contact Traders
Deal with any enquiries from Traders
Detremine LA licence requirements
Notify Traders of LA licence/certificate requirements
Issue contracts
Collect copies of licences and certificates to pass on the LA as required
Liaise with Day Organiser regarding positioning of traders at Assembly areas
Plan Trader space allocations at Assembly
Mark out Trade areas at Assembly
Liaise with Traders during event

## Sponsorship
ACTIONS |  |  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3
| Responsible | Finish | Qu1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4
SPONSORSHIP
Liase with Events Managers/Marketing Manager about British Orienteering centrally obtained sponsors
Prepare Sponsorship leaflet - based on Event
Contact potential commercial sponsors
Get club members to contact potential sponsors they know (worked well for string course prizes)
Obtain Map Sponsors logos for maps
Map sponsors logos to mappers
Promotion of sponsors on website
Collect banners etc from sponsors to use at the event
Arrange with Day Organiser and Equipment team to display banners at events
Promotion of sponsors at event - banners, commentary,
Hospitality tent
Return banners etc to sponsors after event

## Computing & results system
ACTIONS |  |  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3
| Responsible | Finish | Qu1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4
COMPUTING
Results computing contract
Decide if require contract with commercial results provider
Obtain quotes from providers
Place computing contract
Entries and start time allocation
Ensure competitor data files handed over to results company
Print start lists each for day at event
Generate lists for elite
Bibs
Identify if a requirement for race numbers
Identify printer
Confirm requirements / specification for Race numbers
Place order for Race numbers
design content /layout
Any logos obtained
Identify data needed to be printed on race number if any.
test run files from computer
QA bib content (proof?) prior to print run
Print bibs
EOD/Registration
Computing
Enter course/control/class data
Liaise with SI staff during event
Ensure provision of adequate numbers of SI units and SI cards
Oversee initial programming of SI units
Oversee operation of download
Radio controls / commentary
Liaise with Organiser/Planner if Radio controls to be used
If radio controls ensure entry system captures suitable competitor information (part of entry process)
Organise data to make competitor information, linked to radio control ouput, available to comentary team.
PA equipment and Radio controls
Decide requirements and specs
Identify suppiers and obtain quotations
Place orders
Contract commentator
Obtain music performance licence if required
Organise radio controls and liaise with planners/controllers/commentary team over use.
Organise PA delivery to event sites
Oversee PA operation during week

## Results Display
ACTIONS |  |  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3
| Responsible | Finish | Qu1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4
Results
Consider possible results display method
Source results display system.
Periodic results printouts at event
Obtain results display system & transport to event
Liaise with Day organiser to organise results display
Produce prizewinners list

## Enquiries & information
ACTIONS |  |  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3
| Responsible | Finish | Qu1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4
INFORMATION
Respond to e-mail enquiries via web site
Prepare forms and paperwork for Information
Punching start permit cards
Protest / complaint forms
etc
Recruit team for manning Information at Event
Prepare and issue Rota for manning Information point at the Event
Operate registration
Organise Information point
On the day printed information
Identify if this maybe needed
Decide format / design
Identify printer for information sheet
Produce & print information sheet
Distribution at event

## Travel and directions
ACTIONS |  |  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3
| Responsible | Finish | Qu1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4
- Police Liaison
Identify if likely to be any issues need to inform Police about.
Identify point of contact with relevant Police force
Regular updates on event to Police contact
Communicate with police contact on any issues relating to event which police should know about or which require assistance from police.
- Road Signs
Prepare travel directions & list of signs required
Check travel directions with police/Rds Depts if felt necessary
Amend signage requirement after police/rds dept input
Confirm specifications for road signs - Is AA signage necessary
Check confirmed Event Sign Schedule
Check road sign sites (can use Google Earth)
Assess needs for new lettering and logos (or new signs)
Get quotes for lettering / logos (or signs)
Order lettering / logos
Prepare and position signs
Buses
If Bussing required, estimate requirement on range of entry levels.
Identify route - out & back maybe different
Identify turning/parking space at event venues
Plan timings
Compile Bus schedule and specification
Identify bus suppliers
Obtain quotations
Set bus fees
Place contracts
Oversee bus operation during event