BOC Individual 2011 – Team Leaders (version 4.1)

| Title | Team Leader(s) | Deputy | Role Description | Team Members | Equipment | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| Assembly Field |  |  | To build the assembly area including finish and finish funnel in accordance with the agreed plan provided by the Organisers and to dismantle leaving the site as it was found. This will include the putting up and dismantling of SYO, Scout, BOF marquees and 2 SYO tents. To manage vehicle movements on and off assembly field (e.g. traders, PA, toilets, first aid) To tape and sign route to assembly field from car park and remove after the event. Put pile of extra toilet rolls near toilets for self service (keep spares in first aid tent) |  | Scout Marquee (results) SYO Marquee (Enquiries, and colour coded registration) BOF Marquee (BOF and VIP) SYO tent - Prizes tent Tent for finish line camera (M & Ls little tent) EPOC tent – relay registration Tent for first aid Tape (3-4km) Stakes for fencing Mallets Signs within assembly and route to assembly Results boards Finish banner Maps and diagrams for display Clipboard, pens, papers, tape, staples, string, sellotape etc? Spray/flour for marking out Tables, chairs and benches for inside marquees and food court Podium SYO generator (commentary and results use PA generator) Toilet rolls (75) Vehicle Mats Garden pruners to cut back brambles/twigs from entrance lane SYO Banner Labels for tent drop -(Sheffield Wildlife Trust to manage collection of payment and issuing of labels for tents) Bags for map collection at finish | Site visit completed This job requires availability all day on the Friday before the event Traders/suppliers who you will need to direct to their pitch are: Food traders (4+1) Kit traders (3) Toilets Sheffield Wildlife Trust PA van Ian Marsden radio controls First aid Mike Napier to park behind wall behind results tent |
| Car Park |  |  | To minimise damage to parking area as far as possible using mats etc (farmer is particularly concerned about this) To put up and take down roads signs as indicated in the programme so that competitors find the car park. Competitors will be advised to approach in a way which requires only left turns to avoid potential queuing for right turners. Direct First Aid, Traders, Coach etc to entrance to Assembly field if required To arrange the car parking and traffic flow in and out of the car park for all vehicles attending the individual event. To park cars efficiently and quickly so queues do not build up on the public road. To collect £2 car parking fee and hand out final details if required. Hand out Sheffield Wildlife Trust Greno Woods appeal leaflet to each car (800 obtained from Martin, spares to be returned to SWT stall, and by counting returned leaflets we know how many cars we have had). To exit cars efficiently via the same narrow lane that cars will be coming in. Leave car park site as found it Collect in direction signs | Early parking, late starters: Late parking, early starters:- 11.30 ish starts:- | Mats 10 hessian bags 20 bamboo canes 1 roll of red/white tape 15 high visibility vests 4 wooden stakes Road signs: 5 left 5 right 10 straight on Please have £2 car parking ready 2x Warning queuing traffic Welcome to the British Orienteering Championships Bucket for money Fingers for directing | Site visit completed No exit before 1 pm Layout agreed as per Paul diagram. Coach knows where to park 7.30 – 8.30 road signs up 8.30 – team meeting 9.00 – cars start to arrive 12.30 – 1.00 change over 1.00 – first cars allowed to leave 4.30 – 5.30 dismantle and tidy FARMER HAS EXPRESSED CONCERN ABOUT DAMAGE TO THE GRASS. WE HAVE AGREED TO USE MATS IN HIGH USE AREAS AND TO PARK ALL VEHICLES IN SOUTHERN HALF OF THE FIELD. |
| Colour coded registration (sharing tent with Enquiries |  |  | To manage registration for colour coded courses (including staying within map limits and SI hire) at the rate on the published tariff.(liaise with enquiries team leader regarding efficient SI hire/handout process between 2 functions) Two streams/ queues into registration – SI card hire only (see above) and registration (for EoD) . Sell entries – entry forms for EoD, allocate start time and control use of pre printed maps. (colour coded start times will be limited to particular start blocks on white yellow and orange in order to meet championship start requirements) (white, yellow and orange courses are the same courses as some BOC courses) Give runners slip with start time and course for start team for EoD runners. Hand out allocated SI Cards to pre-hired SI Card runners using list provided For EOD SI card hire – record SI number on entry form and charge £1. Keep entry form (with SI card number – own or hired) and send batches of forms to download tent for entry into computer system Check all forms have SI Card number allocated. Control issue of allocated batch of SI Cards – reconcile to pre entered issued list. Hire SI cards for colour coded courses against published tariff (returns will be made to download) |  | Covered area/ marquee space (3mx3m inside) Depending on location of registration 3 X trestle tables 4 X chairs Tape 50m (incl contingency) Piquet’s (metal/ wood) 16 Cash float (change) £30 as £1/ coins. Standard entry forms - Stock (say 100) SI Cards (for hire) incl pre entered Stock (say 50) Notices/ Placards – to CC Registration Notices/ Placards – Pricing/ SI hire/ registration forms Box x (pens/float/etc) 3 Pens 20 Start times lists for pre-entered 4 Start time slips for EoD 60 List of pre allocated SI cards | Site visit not necessary Control descriptions and maps at start (ARE ANY MINOR COURSE MAPS AT REG? WHITE? YELLOW?) – No – all at the start When run out of start slots or maps close colour coded registration (what time does CC Reg open? - 10.30 to 2.30 Entry fees: £4 adult £2 child (no BOF member discount because no levy applied) SI hire fee £1 |
| Co-ordinator |  |  | To co-ordinate all aspects of the overall weekend and deal with issues that effect both days. Host sponsors/VIPs Be available to support Race Day Organiser in event of any issues occurring |  |  |  |
| Commentary |  |  | To make any announcements required by Organiser To announce prizes at prize giving |  |  |  |
| Enquiries, (sharing tent with Colour coded Registration – |  |  | To deal with assorted queries including SI hire, car key store, entry queries etc Contact point for competitors who wish to speak to an event official (need list of mobile numbers) Liaise with Colour Coded registration regarding SI hire process (can have one issue point for both pre-hired cards and EOD hire) Receive complaints and protests and write on form and pass to Organiser (for complaints) and Controller (for protests) Receive payment for lost dibbers (£30) Creoso 2012 (Phillip Jenkins) will be putting a table with leaflets in Enquiries marquee. Find Safety Officer (Colin Best) in event of report of lost competitor/incident Issue warm up maps Sell programmes (£3) Taking orders for results booklets (£2) Register photographers in accordance with BOF policy: http://www.britishorienteering.org.uk/images/uploaded/downloads/governance_policies_osafe.pdf O Safe Policy Appendix D and Template 7: http://www.britishorienteering.org.uk/images/uploaded/downloads/governance_childwelfare_osafeforms.pdf |  | 4 tables 4 chairs Tub for car keys Pens, string, sellotape, hole punch, stapler. Enquiries sign SI cards and form to record SI card number allocated to competitor Programme copies Warm up maps Paper work from Mike Napier Complaints forms Protest forms Cash float Spare programmes for sale Photographer registration form (template 7) List of mobile number | Site visit not possible Jenny will have handled entries in run up to the event. EPOC to man relay registration in separate tent Will be issued with a radio for contacting key officials |
| Equipment - weekend |  |  | Liaise with day equipment officers to ensure sharing and transport of equipment between two days. To include: Toilet rolls BOF marquee tent SYO marquee tent Tables/chairs? Liaise with Arena Team Manager regarding when equipment will be ready for transfer. A club tent transfer service will be offered between 2 days – collect tents from individual and deliver to relay. | None required |  | Site visit unnecessary? This will require the hiring of a van. |
| Equipment – Individual |  |  | To ensure supply, delivery and return of specified equipment for the individual race including BOF equipment Procure/acquire equipment after discussing costs with organiser Maintain master equipment list Liaise with Arena Team Manager for delivery and collection Check equipment before and after use. Replace essential items Synchronise all clocks to BST |  | See list from each team leader. Blank board and pens for adhoc notices Assorted tools etc | Site visit complete This will require the hiring of a trailer Arena will be built on Friday so equipment for this will be required on Friday morning. Organisers plus any others who would like to will camp in Assembly Field for security purposes |
| Forest |  |  | To oversee all requirements in the forest: Organise 4 water stations (man 3 of them) – set up, dismantle, remove rubbish. Brief team on dealing with incidents and alerting Safety Officer if first aid required. Scope does not include Road Crossings, start, finish or assembly. Tape any out of bounds areas (including bird nests) and remove all tapes after event. |  | Tables x4 Chairs Black bin liners Cups (2000?) Water containers (2000x150ml = 300 litres) Sealed all controls map for each drinks point to help locate injured competitors – to be opened only in emergency Mobile phones for contacting assembly Shelter tents? | Site visits complete Possible taping required around bird nests. Tony not available on Friday – need someone on Friday to set up as required |
| Major Events Organiser |  |  | To assist and advice Organisers. |  |  |  |
| Organisers |  |  | To co-ordinate all elements of the organisation for the individual Ensure maps and control descriptions are delivered assembly arena on Friday morning Check correctness of results (inc. DSQ) Decide regarding need for delayed starts and ensure communicated to competitors and team leaders |  | SYO Banner Tent Shelter tent Start and Finish banners Clocks (digital and radio) Programmes |  |
| Permissions |  |  | To secure written permissions for all the areas used by BOC and provide organisers with pack evidencing this |  |  |  |
| Planners |  |  | To plan courses, draw up maps and set out equipment to deliver correct TD courses, the classes are specified in the relevant competition rules and guidelines. Organise printing and bagging of maps and printing of control descriptions (agree number of maps per course with Organiser). Input to risk assessment and liaise with Safety Officer Liaise with SI re. control boxes Agree taping of out of bounds with Forest Team Leader Liaise with Ian Marsden for radio controls. Arrange control collection |  |  |  |
| Postal Entries & entry queries |  |  | To receive postal entries and input into Fabian 4. To handle entry queries and late entries applying the agreed policies. |  |  | Site visit unnecessary |
| Prizegiving |  |  | To co-ordinate the procurement of prizes, accept delivery of recalled trophies and set up and run prize giving ceremonies for individual event, liaising with BOF as required. Identify who is giving out prizes. Use Helen Errington’s Prize Giving Procedure Liaise with PA team to announce winners Co-ordinate un-collected prizes after the event |  | 2 large tables 12 trays Podium Microphone | Site visit completed BOF do recall letters for Trophies. Commentary team to announce winners |
| Programme/Results Booklet |  |  | To pull together the content of the programme and results booklets, proof read and provide content to the website manager and printers for the numbers of requested hard copies. |  |  | Site visit completed Programme needs to be approved by controllers and IOF Advisor |
| Publicity |  |  | Create publicity plan and implement |  |  |  |
| Road crossings |  |  | To marshal the road crossings to facilitate the safe crossing of competitors on the way to the far start and the time out road crossing mid course. This includes putting out appropriate warning signs, tape etc and ensuring that Marshalls are visible to approaching traffic. Collect map exchange maps from arena and put them at map exchange point. Man elite map exchange after second road crossing control |  | Runners crossing signs at least 4 each way Canes Cones Tape High visibility jackets or vests if not available Plywood to make step (not needed now) Carpet to cover barbed wire Maps Map boxes and signs Radio/mobile Bin bags for part one maps | Site visit completed Marshalls are not permitted to stop traffic First part maps dumped by elite competitors to be collected in time for map return |
| Safety |  |  | To assist in ensuring the event is safe and to respond to arising incidents (e.g. injuries, lost competitors, issues with third parties e.g. horses and bikes). To implement the emergency procedure as agreed with the Controller as necessary |  | Emergency shelter tent – Colin purchasing one for BOC and for SYO future use. Radio | Site visit completed Combination code to forest gates will be required. |
| SI/Computing Finish Results SI/computing |  |  | Source and programme SI boxes for planners and starts To work with Michael Napier (leader for SI computing) to provide computing resource. To set up layout within finish marquee in consultation with Michael Napier. Create SI test plan (IOF requirement) Ensure video of finish line (IOF requirement) To give CC Registration & Enquiries forms for entry, list of start slots and map quantities, entry query/change forms To post results on results boards Man map collection from competitors after finish (until 3pm map distribution) Post event, put results on line, route gadget, BOF rankings etc To provide query management, To oversee the finish - managing incidents as required. Collect in hired dibbers (£30 fee for lost dibbers – send to enquiries to pay) To provide services as described in contract |  | Tables Chairs Stationery Other SI and computing kit not provided by Michael Napier SI boxes for planner and starts Clock displaying finish time (SYO has one on order) BOF Finish Sail Banners (M & L have?) Video camera with adequate tape/memory (coming from Oli via Martin) | Site visit completed Have chair for people with punching problems to sit in (helps take heat out of situation) If competitors want to make complaint direct them to enquiries. Direct injured competitors to first aid Direct enquiries re. lost competitor/incidents etc to enquiries |
| Start - South (Wheata) start |  |  | Liaise with Equipment Officer regarding delivery and collection of equipment Ensure maps and control descriptions are taken from arena and delivered to start Collect and return clear, check and start SI boxes from SI Team To plan start layout in conjunction with the organiser and safety officer and in accordance with rules and start procedures. To sign and tape the route to the start To build the start on Friday to agreed layout To oversee the start ensuring that competitors start at the correct time with the correct map, control descriptions etc. To manage late starters and other issues. Note time of late starters (Must ensure all team are fully briefed on late start procedure). To dismantle the start leaving the area as it was found. |  | Sign in assembly pointing to each start Start clocks x2 String of competitor numbers for that start and list of competitors and numbers Safety pins Large sign for gate out of assembly with list of courses and classes and arrows pointing to each start. Large sign with list of course no/s and classes Sign x 2 – check you are going to the right start BOF start sail banners (Martin and Lesley have?) Tape for marking route to start (300m route) 2 “out of bounds to orienteers” signs Late start line sign Course number signs for each lane Tent pegs Start banner Large roll of red/white tape for start lanes (500m) Map boxes 11 Maps and control descriptions, blank maps 4 clip boards Pens, highlighters, stapler, sellotape, paper for making notes Start kite Rubbish bags Sign re shadowing Start lists for competitors (waterproof booklet) Multiple copies of start list by start time including bib number SI boxes – clear , check, start Spare dibbers | Site visit completed Start will be laid out on Friday. |
| Start North (Greno) |  |  | Liaise with Equipment Officer regarding delivery and collection of equipment Collect and return clear, check and start SI boxes from SI Team Ensure maps and control descriptions are taken from arena and delivered to start To plan start layout in conjunction with the organiser and safety officer and in accordance with rules and start procedures. To sign and tape the route to the start To build the start on Friday to agreed layout To oversee the start according to agreed procedure ensuring that competitors start at the correct time with the correct map, control descriptions etc. To manage late starters and other issues. Note time of late starters (Must ensure all team are fully briefed on late start procedure). To dismantle the start leaving the area as it was found. |  | Large sign for gate out of assembly with list of courses and classes and arrows pointing to each start. Large sign with list of course no/s and classes Bear right sign Tape for marking route to start (1.5 km route) plus short lengths for marking route to start 5 out of bounds for orienteers signs Late start line sign Course number signs for each lane Tent pegs Start banner Large roll of red/white tape for start lanes (1000 m) Start clock and call up clock (two new ones on order) Map boxes 18 Maps and control descriptions, blank maps (see Planners) 4 clip boards Pens, highlighters, stapler, sellotape, String of competitor numbers for that start Safety pins Start kites x 2 Start lists for competitors (waterproof booklet) Multiple copies of start list by start time including bib number if possible SI boxes – clear , check, start Clock stand Spare dibbers | Site visit completed Start will be laid out on the Friday Charlie to build 2 m hide |
| String Course |  |  | To design, build, operate, maintain, dismantle |  | Schools SI kit including dibbers String Signs Signs from assembly Sign for String Course Registration tent Large sign “String Course” Signs x 3 (Caution Children Orienteering – no mountain bikes on this area) Tape to stop mountain bikers straying into string course area (500m) Prizes | Site visit completed Using own tent and tables Prizes – sweets and smartwood prizes (liaise with Jenny J) |
| Training Event Organiser |  |  | To run training event |  |  | No timing required. |
| Website |  |  | To update event website. |  |  |  |