## Key actions and Milestones
Version :
Key actions and milestones (see subsidiary sheets for detailed action plans under each heading.
|  |  | Year 1 | [5 empty] | Year 2 | [5 empty] | Year 3
Action | Responsible | Finish | QU1 | QU2 | QU3 | QU4 | S - O | N - D | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O
Event Admin and Finance
Organising Team Meetings | C | On going
Register event with SOA and BOF | AC | 2006-09-01
Recruit Key Roles in Central Organising Team | C | 2007-02-01
Recruit all roles in Central Organising Team | C | 2007-06-01
Complete event Budget | Treas,C, 6 Day | 2008-04-01
Set entry fees | Treas,C,AC.6Day | 2008-06-01
On-line entries live | Ent,Web | 2008-12-01
Entries close | Ent,Web | 2009-06-01
Programmes, bibs and info posted | Team | 2009-07-01
Main Officials debriefing | DP GBJ LW | 2009-10-01
For more details see subsidiary sheet
Entries
Prizes and prizegiving
Orienteering
Select Areas | C, AC + Team | 2006-12-01
Formalise Permissions | AC | 2007-04-01
Confirm Parking and Assembly Areas | AC | 2007-05-01
Allocation of clubs to days | AC, Day C | 2007-12-01
Appointment of Planners and Controllers | AC, Tech C | 2008-06-01
Appointment of Day organisers | AC, Day C | 2008-09-01
Prepare and Issue Day Organisers Manual | Day C | 2008-09-01
Prepare and Issue Technical Manual | Tech C | 2008-09-01
For more details see subsidiary sheet
Training
String Courses
Rest Day Programme
Mapping
Define areas to be mapped | Map | 2008-03-01
Send out mapping tender documents | Map | 2007-06-01
Place mapping contracts | Map | 2007-12-01
Place map printing contract | Map | 2008-12-01
For more details see subsidiary sheet
Event Centre & Campsite
Identify Event Centre and campsite | AC,C | 2006-12-01
Agree Event Centre contract | AC, C | 2007-04-01
For more details see subsidiary sheet
Marketing and Publicity
Event Name | Team | 2006-12-01
Event Logo | Team | 2007-04-01
Advert in 2007 programme | C | 2007-04-01
Publicity at Spey 2007 | C | 2007-08-01
Event website goes live | Web | 2007-07-01
Event Brochure Preparation | M&P | 2008-04-01
Event Brochure Launch | M&P + Team | 2008-05-01
Event Brochure Distribution abroad | M&P | 2008-06-01
Advertising in overseas magazines starts | M&P | 2008-10-01
Brochures to BOF for mailing | M&P | 2008-10-01
For more details see subsidiary sheet
Programme |  |  | see subsidiary sheets
Merchandising |  |  | see subsidiary sheets
Website |  |  | see subsidiary sheets
Equipment |  |  | see subsidiary sheets
Traders contracts |  |  | see subsidiary sheets
Sponsorship |  |  | see subsidiary sheets
Computing |  |  | see subsidiary sheets
Results |  |  | see subsidiary sheets
Information and NewsSheet |  |  | see subsidiary sheets
Travel and Transport |  |  | see subsidiary sheets
Police Liaison |  |  | see subsidiary sheets
Road Signs |  |  | see subsidiary sheets
Buses |  |  | see subsidiary sheets
Socials |  |  | see subsidiary sheets
KEY Each of above headings includes : | Responsibilities - abbreviations
| C | Coordinator
Event Admin and Finance | AC | Assistant Coordinator (SOA Prof Officer)
- Admin | AC (local) | Assistant Coordinator (TAY)
- Finance | Treas | Treasurer
- Competitor mailing | Map C | Mapping coordinator
- Results booklet | Tech C | Technical coordinator
- Debriefing | Day C | Day Coordinator
- Booking toilets | Equip | Equipment Team leader
- Recycling and Refuse | M&P | Marketing and Publicity manager
- Group accommodation | Info | Information team Leader
| Spons mgr | Sponsorship manager
Programme | EC | Event Centre manager
| C'site Mgr | Campsite manager
Entries | Camp book | Campsite bookings organiser
| Man Ent | Manual entries Team Leader
Orienteering | Bus C | Bus coordinator
- Areas | Computing | Computing manager
- Permissions | Ent | Online entries manager
- Mapping | Prog | Programme editor
- Planning | Web | Website manager
- Controlling | Res | Results organiser
- Day Organisation | AC | Poice Liason person (pre 2009 this was done by SOA Profession Officer)
- Training | Training C | Training Coordinator
- String Courses | String C | String Course coordinator
- Rest Day Programme | RS mgr | Road signs organiser
| Socials | Socials programme manager
Mapping | Prizes | Prize and prize giving organisere
| News Ed | News Sheet editor
Entries | Trader mgr | Traders contract manager
| Merch | Merchandise manager
Marketing and Publicity | Rest | Rest Day activities coordinator
- Marketing | Press Off | Press Officer
- Publicity | 6Day | 6 Day Co Director(s)
- Merchandising | Team | Central Organising Team
- Press | Day Orgs | Day Organisers
Web site
Prizes, Certificates and Badges
Equipment
Traders contracts
Sponsorship
Event Centre and Campsite
Computing
- SI liaison
- Results computing
- Management of appeals and protests
- On the day entries
Results
Event Centre and Campsite
Information and NewsSheet
- Event Centre enquiries
- Assembly enquiries
- Daily newssheet
Travel and Transport
- Police Liaison
- Road Signs
- Buses
Socials
Rest Day Activities

## Admin, Finance
0 | 0 |  | Version : |  | 0
0
ACTIONS AND MILESTONES
| Responsible | Finish | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O
Event Admin and Finance
Organising Team Meetings | C | on going
Register event with SOA and BOF | AC | 2006-09-01
Recruit Key Roles in Central Organising Team | C | 2007-02-01
Recruit all roles in Central Organising Team | C | 2007-06-01
Coordinate reviews of Spey 2007 reports/feedback | C | 2007-12-01
List and communicate proposed changes | C | 2007-12-01
Seek approval from 6-day Co for changes | AC, C | 2007-12-01
Ensure changes immplemented | AC,C | 2008-12-01
Complete event Budget | Treas,C,6day | 2008-04-01
Pay bills, maintain accounts | Treaas | on going
Monitor and record income | R Orr, TreasES | on going
Monitor and update budget | Treas, R Orr, C | on going
Set entry fees | Treas,AC, 6Day | 2008-06-01
Set bus fees | Treas,AC, 6Day | 2008-06-01
Set Campsite fees | Treas,AC, 6Day | 2008-06-01
Decide refunds policy and cut off dates | Treas,AC, 6Day | 2008-06-01
Chase up outstanding invoices and expenses | Treas | 2009-09-01
Liase with 6 Day Finance Director to complete post event TB and final accounts | Treas, R Orr | 2009-09-01
Arrange payments to SOA and BO (levy) | Treas, R Orr | 2009-09-01
Disbursement of profits to clubs | Treas, R Orr | 2009-09-01
Info emailed or posted to overseas competitors | Team | 2009-07-01
Info emailed or posted to UK competitors (not at home in July) | Team | 2009-07-01
All remaining UK Programmes, bibs and info posted | Team | 2009-07-01
Main Officials debriefing | C, AC | 2009-10-01
Toilets
Decide spec. | AC | 2008-04-01
Obtain quotations | AC | 2008-04-01
Place contract | AC
Site visit with Scotloo | AC
Monitor implementation | AC
Recycling/Refuse
Decide spec. - EC, Campsite and event sites | AC
Obtain quotations | AC
Place contract | AC
Monitor implementation | AC
Group Accommodation
Identify suitrable accommodation and contacts | Team
Put info on group accommodation on web site | Web
deal with requests for Gp Accom. | Info

## Programme
Proposed Timetable for Production of Programme
| Responsible | Finish | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  |  | May |  |  |  | June |  |  |  | July
|  | w/e | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15
Appoint Printer & Agree Copy Date | Prog Ed | 2009-01-14
Draw-up List of Contributors | Prog Ed, AC,C
Agree Timetable for Preparing Copy | Prog Ed | 2009-01-21
Inform Contributors of Process | Prog Ed | 2009-01-28
Agree Content of Contributions | Prog Ed + Team | 2009-02-18
Day officials & other team leaders to agree arrangements for coordination & submission of copy | Central Team and Day teams | 2009-02-18
Preparation of Copy within teams | Central Team and Day teams | 2009-04-15
Copy to Prog. Editors | Central Team and Day teams | 2009-04-15
Programme Editors chase late Copy & check received Copy | Prog Ed | 2009-04-29
Advertising Copy to Prog. Editors | Spons | 2009-04-25
Cut-off date for draft copy |  | 2009-04-25
* Send Draft Programme to contributors | Prog Ed | 2009-05-01
* Comments back on Draft Programme | Central Team and Day teams | 2009-05-12
Final Version Distributed for checking | Prog Ed | 2009-06-03
Proof read final copy | Prog ED, AC, C Info
Agree Final Copy & Number required | Prog Ed + Team | 2009-06-15
Submit Copy to Printers | Prog Ed | 2009-06-13
Sign off printers proof | Prog Ed | 2009-06-24
Printed Programmes Returned | Printer | 2009-07-01
Envelope Programmes & Post | Info + Team | 2009-07-08
* In 2009 these two steps were dispensed with for most Programme sections.

## Entries
0 | 0 |  | Version : |  | 0
0
ACTIONS AND MILESTONES | [14 empty] | 2009
| Responsible | Finish | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O
ENTRIES
Review Spey 2007 report | Ent,C,Comp | 2007-10-01
Set entry system specification (+ outputs) | Ent,C,Comp | 2007-12-01
Investigate online entry system providers | Ent | 2008-04-01
Propose provider | Ent | 2008-04-01
Decide provider | Ent, C, Team | 2008-06-01
Place contract with specifications | Ent | 2008-06-01
Design paper entry system | Man Ent,Ent,Comp | 2008-09-01
Trail run / test of entry system | Ent,C,Comp | 2008-09-01
On-line entries live | Ent, Web | 2008-12-01
Monitor system operation | Ent | on going
Deal with any refund requests | Ent, Treas | on going
Report at first cut off date | Ent | 2009-01-01
Deal with paper entries and enter data | Man Ent | on going
Final number estimate from entry at first cut off | Ent | 2009-01-01
Report at second cut off date | Ent | 2009-04-01
Plan provision of entry data to computing | Ent, Comp | 2009-04-01
Entries close | Ent | 2009-06-01
Specify requirements for start time allocation system | Ent Computing
Set up start allocation system | Ent Computing
Allocate start times | Ent
Ensure all special requests related to start times dealt with | Ent
Publish start lists on website | Ent Web
Deal with enquiries and change request after start lists published | Ent, Computing
Provide data to computing for SI database | Ent, Computing
Provide data to computing for bibs, labels | Ent | 2008-07-07
Final numbers to mapping coordinator | Ent
Deal with an late entries | Ent Computing
Plan registration system for EOD | Man Ent, Comp | 2009-05-01
Recruit and train EOD /registration team | Man Ent | 2009-07-01
Organise EOD/reegistration rota for event | Man Ent | 2009-07-01
Oversee operation of EOD system at event | Man Ent | at event
Deal with change requests | Ent, Man Ent | 2009-07-01
Monitor and manage Bus bookings | Bus C | 2009-06-01
Monitor and manage Campsite bookings | Camp Book | 2009-06-01

## Orienteering Training & String
0 | 0 |  | Version :
0
ACTIONS AND MILESTONES | [14 empty] | 2009
| Responsible | Finish | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O
Orienteering
Note - detailed actions of planners and controllers are in Technical Manual
Note - detailed actions of organisers are in Organisers Manual
Select Areas | C, AC | 2006-12-01
Formalise Permissions | AC | 2007-04-01
Confirm Parking and Assembly Areas | AC | 2007-05-01
Define areas to be mapped | AC,C | 2007-09-01
Allocation of clubs to days | AC,C | 2008-01-01
Decide details of description hand out at start | Day C | 2008-09-01
Appointment of Planners and Controllers | Tech C, AC | 2008-06-01
Prepare Area Info pack, including landowner contact details, access details, constraintsand restrictions, sketch maps showing area, assembly, parking for planners, controllers and day organisers | AC | 2008-06-01
Distribute info packs to planners, controllers and day organisers | AC | on going
Appointment of Day organisers | Day C, AC | 2008-09-01
Compile and maintain contact list of Day Officials | AC | 2008-09-01
Prepare and Issue Day Organisers Manual | Day C | 2008-09-01
Update Day Org Manual as necessary | Day C | on going
Monitor Day Org progress against timetable in manual | Day C | on going
Prepare and Issue Technical Manual | Tech C | 2008-06-01
Update Tech Manual as necessary | Tech C | on going
Monitor Planning and Controlling progress against timetable in manual | Tech C | on going
Confirm Elite format | C, AC, Team | 2008-06-01
Define Condes version to be used and place template on web | Tech C, Web | 2008-06-01
Arrange Condes training if needed | Tech C | 2008-10-01
Decide if radio controls to be used (all days) | Team | 2008-09-01
Decide sites for Radio controls | Tech C, AC | 2009-04-01
Monitor entry numbers against courses (240 max) | Ent & Tech CDC | on going
Assess help needed on each day from non Scottish clubs | Day C | 2009-05-01
Email entrants seeking voluntreers for on the day help | Ent, Day C | 2009-06-01
Allocate non SOA club helpers to days | Day C | 2009-07-01
Define requirements for production of description sheets | Tech C | 2008-11-01
Arrange production of description sheets with map printing | Map | 2009-01-01
Description sheets delivered to event centre | Printer | 2009-07-27
0 | 0 |  | Version : |  | 0
0
ACTIONS AND MILESTONES |  | 0 | [6 empty] | 0 | [5 empty] | 2009
| Responsible | Finish | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O
TRAINING
Review Spey 2007 Reports | Training C | 2007-12-01
Proposed training programme for 2009 | Training C | 2008-04-01
Decide training to be provided for 2009 | Org Team | 2008-04-01
Identify training areas | Training C | 2008-04-01
Assess quality of maps of identified areas | Training C | 2008-12-01
Arrange update of maps as necessary | Training C | 2008-12-01
Plan distribution of training packs | Training C | 2009-04-01
Plan training courses | Training C | 2009-05-01
Ensure parking provision at venues | Training C | 2009-02-01
Organise any coaching provision | Training C | 2009-05-01
Prepare training packs | Training C | 2009-06-01
Arrange distribution points for training packs | Training C | 2009-05-01
Liase with Information Team Leader on distribution of training packs at Info point during event | Training C Info | 2009-07-01
Distribute training packs | Training C | 2009-07-01
Place controls | Training C | 2009-07-01
Monitor availability of packs | Training C | At event
Remove controls | Training C | After event
STRING COURSES
Review Spey 2007 Reports | String C | 2007-10-01
Decide String Course parameters for 2009 | String C | 2008-03-01
Prepare String Course guidelines | String C | 2008-08-01
Distribute guidelines to Day Organisers | String C | 2008-09-01
Arrange provision of string course equipment | String C | 2009-07-01
Identify String Course Areas | Day Org's | 2009-03-01
Prepare String Course maps | Day Org's | 2009-06-01
Monitor planning/organisation of String Courses | String C | on going
Day controllers check and approve string courses | Controllers | 2009-05-01
Arrange distribution of string course prizes to each day | String C | at event
Facilitate handing over of Sring Course equipment from each day to the next day. | String C | at event

## Mapping
0 | 0 |  | Version : |  | 0
0
ACTIONS AND MILESTONES | [14 empty] | 2009
| Responsible | Finish | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O
Mapping
Review Prev 6 days mapping and map printing timetable | Map | 2007-09-01
Decide mapping and map printing timetable | Map | 2007-09-01
Communicateand agree timetable with Tech coordinator and Day coordinator | Map, Tech C, Day C | 2007-12-01
Define areas to be mapped | Map | 2008-03-01
Send out mapping tender documents | Map | 2007-06-01
Place mapping contracts | Map | 2007-12-01
Place map printing contract | Map | 2008-12-01
Draft map to planners and controllers | Map | 2008-07-01
Ensure survey of summer vegetation | Map | 2008-08-31
Map corrections from planners/controllers | Planners & Controllers | 2009-04-01
Map corrections to mappers | Map | 2009-04-01
Design map layouts including logos | Map, Mappers | 2009-03-01
Get quotations/tenders for map printing | Map | 2009-01-01
Place map and description sheet printer contract | Map | 2009-01-01
Condes file to printer for proofing | Controllers | 2009-04-19
First digital proof to planners/controllers | Printer | 2009-04-30
Info on map sizes to programme & web site | Map, Prog Ed, Web
Comments on first proof to printer | Controllers | 2009-05-19
Final digital proof to Planners/Controllers | Printer | 2009-06-02
Controllers approve final digital proofs | Controllers | 2009-06-16
Print numbers for each course to printer | Map | 2009-06-30
Maps printed, copy of each to planners/controllers | Printer | 2009-07-13
Planners & Controllers check paper copy | Planners & Controllers | 2009-07-20
Any problems notified to Mapping coordinator | Planners & Controllers | 2009-07-20
Actions taken to rectify view of any problems | Map | 2009-07-20
Bulk of maps delivered to Event Centre | Printer | 2009-07-27

## Marketing and Publicity
0 | 0 |  | Version : |  | 0
0
ACTIONS AND MILESTONES | [14 empty] | 2009
| Responsible | Finish | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O
Marketing and Publicity
Event Name | Team | 2006-12-01
Event Logo | Team | 2007-04-01
Advert in 2007 programme | C | 2007-04-01
Publicity at Spey 2007 | C | 2007-08-01
Event Brochure Preparation |  | 2008-04-01
Decide when to launch brochure | Org Team | 2007-09-01
Decide Brochure format (folded A4 or A3) | Org Team | 2007-12-01
Design Brochure | M & P | 2007-12-01
Collect all input to brochure | M & P | 2008-01-01
Identify printer for brochure | M & P | 2008-02-01
Prepare artwork for brochure | M & P | 2008-02-01
Arrange printing of brochure | M & P | 2008-03-01
Event Brochure Launch | Org Team | Mar/Apr 08
Arrange Brochure distribution at UK events | M & P | 2008
Arrange Brochure Distribution abroad | M & P | Summer 08
Distribute Brochures in Score | M & P | 2008-05-01
Advert in Croeso 08 Programme | M & P
Brochure and display at Croeso 08 | M & P
Advertising in overseas magazines starts | M & P | 2008-10-01
Brochures to BOF for mailing | M & P | 2008-10-01
BOF mail brochures with renewal forms | M & P | 2008-11-01
Get foreign clubs e-mail info (Marion McCormack) | JW | done for 2007 but not for 2009
Write brief publicity e-mail | JW | done for 2007 but not for 2009
Get translations into appropriate languages | JW | done for 2007 but not for 2009
Send to foreign clubs | JW | done for 2007 but not for 2009
Press reports
Regular column in SCORE | C AC | various
Article in CompassSport | Press Off | various
Article in Focus (British Orienteering) | Press Off | 2008-10-01
Establish contacts with local and national media | Press Off | 2009-03-01
Press releases to local papers | Press Off | on going
Press releases to National papers | Press Off | on going
Press releases during the event - results and stories | Press Off | at event
Post event press releases | Press Off | 2009-08-01
Merchandising
Appoint Merchandising manager | GBJ | 2007-12-01
Decide on merchandising range of goods | Org Team | 2008-10-01
Decide merchandise budget | C Merch | 2008-10-01
Decide if Org Team to have free identifying polo shirt | Org Team | 2008-10-01
Investigate on line sales | Merch | 2008-10-01
Implement online sales if chosen route | Merch | 2008-11-01
Design and specifications for merchandise | Merch | 2009-02-01
Identify suppliers for merchandise | Merch | 2009-02-01
Arrange production and delivery of merchandise | Merch | 2009-06-01
Plan sale at event of merchandise | Merch | 2009-06-01
Organise sale of merchandise at event | Merch | at event

## Website
0 | 0 |  |  | Version : |  | 0
0
ACTIONS AND MILESTONES
| Responsible | Information | Finish | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O
Provider
WEBSITE and RESULTS
Event website goes live | Web |  | 2007-08-01
Develop website based on feedback from 2007 | Web |  | on going
Add information as available | Web
Entry fees | Web | Ent | 2008-09-01
Date for entries opening | Web | Ent | now
Cut off dates for low entry fees - with reminders as dates approach | Web | Ent | on going
Info on refunds and cut off dates | Web | Ent | 2008-09-01
Info on making changes to entries | Web | Ent | 2008-09-01
Info on postal entries | Web | Ent | 2008-09-01
P O Box - postal entries and enquiries | Web | Ent | 2008-04-01
Classes and approx course lengths | Web | Tech C | 2008-09-01
Campsite fees and details | Web | C'site mgr | 2008-09-01
Bus fees and details | Web | Bus C | 2008-09-01
Accommodation info (e.g for groups) | Web | Info | 2008-09-01
Colour coded course explanation | Web | Tech C | 2008-09-01
Info on EOD | Web | Man Ent | 2008-12-01
Training Programme details | Web | Training | 2008-12-01
Rest Day Events | Web | Rest | 2009-02-01
Info an Social activities | Web | Socials | on going
Map sales at event | Web | Info | 2009-06-01
Link to entry system | Web | Ent | 2008-11-01
Tech Manual on website | Web | Tech C | 2008-06-01
Organisers Manual on website | Web | Day C | 2008-09-01
Info to Day Oficials on how to access Org and Tech Manuals | Tech C Day C |  | 2008-06-01
Updates to Org and Tech Manuals | Web | Tech C Day C | on going
Programme posted on website | Web | Ent | 2009-07-01
Start lists | Web | Ent | 2009-07-01
Rest Day events information on site - locations - timings - coaching - how to enter | Web | Rest | on going
Links to other sites as appropriate | Web |  | on going
Sponsor adverts and logos | Web | Spons | on going
RESULTS on website
pre-event trial uploading to website | Web | Res | 2009-06-01
daily download to website at event | Web | Res | at event
Info on Route Gadget and links on website | Web | Res | 2009-06-01

## Prizes, Certificates & Badges
0 | 0 |  | Version : |  | 0
0
ACTIONS AND MILESTONES
| Responsible | Finish | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O
PRIZES and PRIZEGIVING
Decide what prizes to award | Org Team | 2008-04-01
Decide on main officials momentos | Org Team | 2008-04-01
Proposals on suitable prizes | Prizes | 2008-08-01
Accept proposal on prizes | Org Team | 2008-08-01
Obtain samples of prizes | Prizes | 2008-12-01
Confirm prizes are suitable | Org Team | 2008-12-01
Order prizes | Prizes | 2009-03-01
Arrange design version of logo for coaster | Prizes | 2008-08-01
Sample of coaster | Prizes | 2009-03-01
Order coasters | Prizes | 2009-04-01
Plan prizegiving | Prizes | 2009-05-01
Organise delivery of prizes and coasters | Prizes
Organise getting prizes and coasters to Day 6 event | Prizes
Organise people to give prizes | Prizes | 2009-07-01
Source staging for prizegiving | Equipment team | 2009-07-01
Ensure PA system suitable for prizegiving | Prizes | 2009-07-01
Publicise and manage spot prizes (donated by sponsors) | Prizes
Prizewinners lists from computing | Computing | at event
Run Prizegiving | Prizes | at event
CERTIFICATES
Produce certificate template | Computing | 2009-04-01
Organise extracts from maps of each day | Map C | 2009-04-01
Produce certificate blanks | Computing | 2009-07-01
Print certificates days 1 - 5 (only) | Computing | at event
Certificates at next day's Info tent | Info | at event
Info on certificate availability in NewsSheet | News Ed | 2009-08-02
Day 6 - NO certificates - info in Programme | Info | 2009-04-01
CLOTH BADGES
Design badge (use 2007 as template) | Prizes | 2009-04-01
Decide numbers to order (250G,175S&175B) | Prizes | 2009-04-01
Order badges (Recognition Express) | Prizes | 2009-04-01
Ensure clear criteria for badge standards | Prizes | 2009-07-01
Publicise badge standards | Prizes News Ed | at event

## Equipment
| 0 |  | Version : |  | 0
0
ACTIONS AND MILESTONES
| Responsible | Finish | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O
EQUIPMENT
Review Spey 2007 Reports | Equip | 2007-12-01
Decide how to organise equipment team | Equip | 2008-04-01
Recruit equipment team members | Equip | 2008-12-01
Info on equipment in Day Organisers Manual | Equip Day C | 2008-06-01
Info on equipment in Technical Manual | Equip Tech C | 2008-04-01
Collect information on Day needs | Day C Tech C Equip AC | 2009-04-01
Order water for finish (Day 1 only) | Equip | 2009-06-01
Arrange van/vehicle hire | Equip | 2009-06-01
Check equipment stocks in store | Equip | 2009-04-01
Order any extra equipment needed | Equip | 2009-05-01
Ensure material available for stiles/bridges | Equip | 2009-04-01
Erect stiles and bridges | Equip | 2009-07-01
Deliver eqiupment to event sites | Equip | 2009-07-01
Deliver water etc to on course drinks points | Equip | at event
Deliver maps to starts | Equip | at event
Source staging for prizegiving | Equip | 2009-06-01
Position staging for prizegiving | Equip | at event
Brief team on roles/ tasks for week of event | Equip | 2009-07-01
Collect equipment from Glenmore store | Equip | 2009-07-01
Deliver equipment to each event site | Equip | at event
Advise Day teams as necessary on erection of equipment | Equip Day teams | at event
Load up equipment at end of each day event to transfer to next site | Equip Day teams | at event
After event, recover equipment, sort and return to store | Equip | 2009-09-01
Generators
Decide requirements and specs | Equip Computing | 2009-04-01
Identify suppiers and obtain quotations | Equip | 2009-05-01
Place orders | Equip | 2009-05-01
Deliver to event sites and oversee operation | Equip | at event
2-way Radios
Decide requirements and specs | AC | 2009-04-01
Assess 6 Day stocks to decide if adequate | AC | 2009-04-01
Procure any extra radios needed | AC | 2009-06-01
Organise delivery to event sites and manage issue, return and recharging | AC | at event
PA and Radio Controls - see Computing

## Trader Contracts
0 | 0 |  | Version : |  | 0
0
ACTIONS AND MILESTONES
| Responsible | Finish | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O
TRADERS CONTRACTS
Review Spey 2007 Reports | Trader mgr | 2007-12-01
Set Traders fees | Org Team | 2008-08-01
Amend contracts used in 2007 if necessary | Trader mgr | 2008-10-01
Contact 2007 Traders re 2009 | Trader mgr | 2008-12-01
Deal with any enquiries from Traders | Trader mgr | on going
Detremine LA licence requirements | Trader mgr | 2009-04-01
Notify Traders of LA licence/certificate requirements | Trader mgr | 2009-05-01
Issue contracts | Trader mgr | 2009-06-01
Collect copies of licences and certificates to pass on the LA as required | Trader mgr | 2009-07-01
Liaise with Day Organisers regarding positioning of traders at Assembly areas | Trader mgr | 2009-07-01
Plan Trader space allocations at Assemblies | Trader mgr | 2009-06-01
Mark out Trade areas at Assemblies | Trader mgr | at event
Liaise with Traders during event | Trader mgr | at event

## Sponsorship
0 | 0 |  | Version : |  | 0
0
ACTIONS AND MILESTONES
| Responsible | Finish | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O | N - D | J - F | M - A | M - J | J - A | S - O
SPONSORSHIP
Review Spey 2007 Reports | AC C Sponsor Mgr | 2007-10-01
Agree who will look after Public body sponsorship - could be sponsorship mgr or could be AC or C | AC C Sponsor Mgr | 2007-10-01
Approach Local Authority re Leader support (maps?) | AC C | 2007-09-01
Complete Leader application | AC | 2007-12-01
Approach Event Scotland re support for event | AC C | 2008-02-01
Complete Event Scotland application | AC | 2008-06-01
Approach FC re map sponsorship | AC C | 2007-11-01
Complete FC application | AC | 2008-03-01
Approach Local Authority re sponsorship (maps, socials, marketing?) | AC C | 2007-11-01
Complete LA application | AC | 2008-02-01
Prepare Sponsorship leaflet - based on Brochure | Sponsor Mgr | 2008-04-01
Contact potential commercial sponsors | Sponsor Mgr | Q3/4 08
Scottish Coop | Sponsor Mgr | Q3/4 08
Rock and Run | Sponsor Mgr | Q3/4 08
etc | Sponsor Mgr | Q3/4 08
Get club members to contact potential sponsors they know (worked well for string course prizes) | Sponsor Mgr
Obtain Map Sponsors logos for maps | Sponsor Mgr | 2009-04-01
Map sponsors logos to mappers | Sponsor Mgr | 2009-04-01
Sponsors adverts for programme | Sponsor Mgr | 2009-04-01
Promotion of sponsors on website | Web, Sponsor mgr | on going
Collect banners etc from sponsors to use at the event | Sponsor Mgr | 2009-07-01
Arrange with Day Organisers and Equipment team to display banners at events | Sponsor Mgr, Day Organisers | 2009-07-01
Promotion of sponsors at event - banners, commentary, Daily Newssheet | Sponsor Mgr, Day Organisers | at event
Hospitality tent Day 1 - WRE (or D4 - 100th event) | PH Org Team | 2009-08-01
Return banners etc to sponsors after event

## Computing & results system
ACTIONS |  |  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3
| Responsible | Finish | Qu1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4
COMPUTING
Results computing contract
Decide if require contract with commercial results provider
Obtain quotes from providers
Place computing contract
Entries and start time allocation
Ensure competitor data files handed over to results company
Print start lists each for day at event
Generate lists for elite
Bibs and envelope labels
Identify requirement for race numbers
Identify printer
Confirm requirements / specification for Race numbers
Place order for Race numbers
design content /layout
Any logos obtained
Identify data needed to be printed on race number if any.
test run files from computer
QA bib content (proof?) prior to print run
Print bibs
Decide data to go on address labels
Produce address labels for envelopes
Labels and Bibs to envelope stuffing session
EOD/Registration
Compuiting (continued)
Orienteering
Enter course/control/class data
Liaise with SI staff during event
Ensure provision of adequate num,bers of SI units and SI cards
Oversee initial programming of SI units
Manage collection, reprogramming and handing on of SI units from day to day
Oversee operation of download
Ensure any SI or computing related problems resolved
Radio controls / commentary
Decide if Radio controls to be used (D4 & D6 ?)
If radio controls ensure entry system captures suitable competitor information (part of entry process)
Organise data to make competitor information, linked to radio control ouput, available to comentary team.
PA equipment and Radio controls
Decide requirements and specs
Identify suppiers and obtain quotations
Place orders
Contract commentator
Obtain music performance licence
Organise radio controls and liaise with planners/controllers/commentary tem over use.
Organise PA delivery to event sites
Oversee PA operation during week

## Results Display
ACTIONS |  |  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3
| Responsible | Finish | Qu1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4
Results
Consider possible results display method
Source results display system.
Decide if results display system required for Event Centre
Periodic results printouts at event
Obtain results display system & transport to event
Liaise with Day organiser to organise results display at each day
Ensure previous day results and start lists displayed each day
Dismantle results system & transfer if required next day
Organise display of results if required at Event Centre
Produce prizewinners list

## Event Centre & Campsite
ACTIONS |  |  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3
| Responsible | Finish | Qu1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4
Event Centre
Identify Event Centre
Agree Event Centre contract
Appoint Event Centre Manager
Review Event Centre contract with EC manager
Meet with Event Centre owners and EC manager to review facilities
Sign Event Contract and pay deposit
Meet at Event Centre with other key members of Org team (Info, EOFD, Computing) to review facilities and agree exact layout and room allocation
Detailed planning of EC set up and operation
Risk Assessment for Event Centre
Prepare signs needed for Event Centre
Organise EC set up
Organise EC operation
Organise EC clear up
CAMPSITE if required
Appoint Campsite Manager
Decide extra facilities required for campsite
Investigate suppliers of facilities
Arrange hire of facilities required
Arrange installation of facilities (plumber, electrician)
Decide campsite charges
Campsite booking info to entry system
Monitor campsite bookings
Detailed planning of layout of Campsite
Put Campsite information on event website
Risk assessment for campsite
Agree fire safety requirements with Local Fire Officer
Compile rules for campsite
Decide security for campsite
Decide management of youth campsite and potential behaviour problems
Publicise campsite rules on event website
plan system for campsite registration
Communicate regsitration process to prospective campers (website, Programme)
Supply campsite information for Programme
Campsite layout for Programme
Confirm EC/Campsite facilities and publicise in Programme and Web site
Layout campsite
Oversee installation of facilities
Operate campsite registration
Oversee campite operation during event
Clear up campsite

## Enquiries & information
0 |  |  | 0 |  | 0
0
ACTIONS |  |  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3
| Responsible | Finish | Qu1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4
INFORMATION
Respond to e-mail enquiries via web site
Prepare forms and paperwork for Information
Punching start permit cards
Protest / complaint forms
etc
Recruit team for manning Information at Event
Prepare and issue Rota for manning Information point at the Event
Organise Envelope filling session - Programmes, Bibs and hire cards
Write information email to overseas competitors - with registration details
Organise posting of bibs and Programmes to UK competitors
Operate registration (programmes, bibs and hire cards) for overseas competitors and UK competitors not receiving them by post at event centre
Organise Information point at each day event and in evening at Event Centre
On the day printed information
Identify if this maybe needed
Decide format / design
Identify printer for information sheet
Produce & print information sheet
Distribution at event

## Travel and directions
0 |  |  | 0 |  | 0
0
ACTIONS |  |  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3
| Responsible | Finish | Qu1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4
- Police Liaison
Identify if likely to be any issues need to inform Police about.
Identify point of contact with relevant Police force
Regular updates on event to Police contact
Communicate with police contact on any issues relating to event which police should know about or which require assistance from police.
- Road Signs
Prepare travel directions & list of signs required
Check travel directions with police/Rds Depts if felt necessary
Amend signage requirement after police/rds dept input
Confirm specifications for road signs - Is AA signage necessary
Check confirmed Event Sign Schedule
Check road sign sites (can use Google Earth)
Assess needs for new lettering and logos (or new signs)
Get quotes for lettering / logos (or signs)
Order lettering / logos
Prepare and position signs
Buses
If Bussing required, estimate requirement on range of entry levels.
Identify route - out & back maybe different
Identify turning/parking space at event venues
Plan timings
Compile Bus schedule and specification
Identify bus suppliers
Obtain quotations
Set bus fees
Place contracts
Oversee bus operation during event

## Social
0 | 0 |  | Version : |  | 0
0
ACTIONS |  |  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3
| Responsible | Finish | Qu1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4 | QU1 | QU2 | QU3 | QU4
SOCIALS
Review previous event
Review EC facilities
Outline plans and proposals for socials
Review proposals and confirm plans
Agree budget for socials
Identify providers/suppliers
Make necessary bookings - suppliers
Make necessary bookings - facilities
Publicise socials on website
Publicise socials in programme
Produce tickets as required for socials
Liase with Info Team Leader on sales of tickets
Arrange volunteers to help at socials
Oversee Social programme